# REPORTING GUIDELINES FOR GRANTEES

General: This template is to provide reporting guidelines for all grantees of the Africa Transitional Justice Legacy Fund (ATJLF). It is meant to provide a framework for documenting and reporting on major outcomes and impacts of the project at the end of the project. The ATJLF expects honest and accurate representation of outcomes linked to funded activities implemented as part of the project. The reporting template is attached as Annex A (for the project narrative). In addition to the Final Narrative Report, the Project Logical Framework must also be completed with data on outcomes and outputs and other specifics required in the document.

Timelines: For the Initiative for Transitional Justice in Africa project, the Fund expects grantees to report a total of four times: an inception report, a first-quarter report, a second-quarter report and a final report. The Inception Report is expected to be submitted three (3) months after Project Launch. The first quarter Report should be submitted no later than six (6) months into project implementation, the second quarter Report is expected 9 months into project implementation while the Final Report should be submitted a maximum of five weeks after project completion. These constitute the contractual obligations of the grant agreement. All reports should be submitted to the Secretariat as indicated in the grant agreement (except otherwise stated). However, we expect grantees to also send to the ATJLF Secretariat, regular updates/reports on major outputs and changes in the project. These should come in the form of post-event briefings, beneficiary stories, and monthly reports/updates; be no more than two (2) pages long and should focus on outputs and verifiable or tangible outcomes from the project as well as general updates on TJ trends in the country.

Person (s) Responsible: All grantees should provide the name and contact details of one person who will be responsible for submitting all reports to the ATJLF. This person is expected to be directly involved in both programmatic and operational issues of the project and must be in a position to provide clarifications, response to queries, and additional information as and when required. In the absence of this person, all grantees are expected to inform the ATJLF Secretariat immediately, and prior to reporting deadlines. #

Report Sections:

- ASSESSMENT OF THE MONTHS 9 – 12 OF PROJECT IMPLEMENTATION

- ASSESSMENT OF OVERALL PROJECT

- ASSESSMENT OF THE RELATIONSHIP WITH THE ATJLF

- ASSESSMENT OF THE RELATIONSHIP WITH OTHER ATJLF GRANTEES AND LOCAL AUTHORITIES

- The LOGICAL FRAMEWORK

Specific Expectations: The ATJLF expects the final reports to have the following specifics:

- Activity or outputs: all budgeted activities undertaken as part of the project. These should be in line with outputs determined by the logical framework agreed upon with the partner prior to project commencement.

- Outcomes (direct or indirect): this refers to any impact or result that emanated from an implemented activity. This includes any unexpected outcomes.

- Changes (if any): any variations or deviations from what was proposed or planned. If change is significant and will have budgetary implications, the ATJLF Secretariat must be informed prior. If the changes are minor and with no significant budgetary implications, all grantees are expected to report on them, with a corresponding explanation.

- Challenges: this refers to challenges encountered during the implementation of project activities within the reporting period.

- Learning: all learning (positive, programmatic or otherwise) should be documented and shared with the ATJLF Secretariat. This includes unexpected learnings

- Suggestions for ATJLF

- Any additional funding received which supports or complements the work

- A summary of what difference ATJLF funding has made to transitional justice in your country

ANNEX A: PROJECT FINAL NARRATIVE REPORT

| NAME OF ORGANISATION | Invisible Women Inclusion Network (I-WIN) |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| PROJECT TITLE | Victim Participation in Truth, Justice, Reconciliation and Accountability Process through Formation of the VSG. |  |  |  |  |
| COUNTRY OF OPERATION | SOUTH SUDAN |  |  |  |  |
| REPORTING PERIOD | FROM | August 2025 | TO | April 2026 |  |
| DATE OF SUBMISSION | 30/04/2026 |  |  |  |  |
| RESPONSIBLE PERSON | Immaculate Aciro |  | CONTACT DETAILS | info@i-win-ssd.org ¦ ed@i-win-ssd.org +211925914488/+211922944423 |  |
| SIGNATURE |  |  | DATE SIGNED | 04/05/2026 |  |
| - ASSESSMENT OF THE MONTHS 9 – 12 MONTHS OF PROJECT IMPLEMENTATION |  |  |  |  |  |
| - Please outline and describe below, all key activities you undertook as part of this project in the period under review? (please feel free to add as appropriate) Include link to pictures from each activity listed. In this section, grantee should also highlight and describe how many beneficiaries were reached directly and indirectly specifying how many were women. |  |  |  |  |  |
| During the reporting period, Invisible Women Inclusion Network (I-WIN) implemented a comprehensive package of survivor-centred and community-based activities aimed at strengthening victim participation, psychosocial healing, community awareness, and leadership accountability in Transitional Justice (TJ) processes in Rubkona County and Bentiu IDP Camp, Unity State. The activities implemented are outlined below. |  |  |  |  |  |
| ### 1.1 Official Project Launch | I-WIN successfully conducted the official project launch on 11 August 2025 in Rubkona County. The launch introduced the project objectives, scope, and survivor-centred approach to key stakeholders, including state and county authorities, UN agencies, civil society organisations, women and youth groups, persons with disabilities, IDPs, returnees, and religious leaders. The launch enhanced coordination, strengthened stakeholder buy-in, and secured public commitment from local leaders to support survivor participation in truth-telling, reconciliation, and accountability processes linked to the Commission for Truth, Reconciliation and Healing (CTRH). - Direct beneficiaries: 50 participants (30 women, 20 men) - Indirect beneficiaries: ~500 community members (approx. 60% women) Photo link: https://docs.google.com/document/d/1-ht8ZG6F0u8KKHyLzonSl-MTAriF07YL/edit?usp=sharing&ouid=106912853763388518804&rtpof=true&sd=true |  |  |  |  |
| ### 1.2 Establishment and Strengthening of Victim Support Groups (VSGs) | ### The project established and strengthened 50 functional Victim Support Groups (VSGs) across Bentiu IDP Camp, Rubkona, Pakur, Shilak, Makuai, Yoanyang, and surrounding communities. The VSGs served as safe, survivor-led spaces for psychosocial support, peer counselling, truth-telling preparation, stigma reduction, and advocacy for justice and reparations. Survivors participated voluntarily under confidentiality and safeguarding principles, with deliberate prioritisation of women survivors of sexual and gender-based violence (SGBV), persons with disabilities, IDPs, returnees, youth, elderly survivors, and caregivers of children born of conflict. - Direct beneficiaries: 700 survivors (approx. 455 women and girls, ~65%) - Indirect beneficiaries: ~6,500 community members reached through peer dissemination (approx. 60% women) Photo link: https://docs.google.com/document/d/1rfnLMWZKxw0GrZhN-Cre8u9-zkq_MxIC/edit?usp=sharing&ouid=106912853763388518804&rtpof=true&sd=true https://docs.google.com/document/d/1rfnLMWZKxw0GrZhN-Cre8u9-zkq_MxIC/edit?usp=sharing&ouid=106912853763388518804&rtpof=true&sd=true https://docs.google.com/document/d/1xee1geqA1ibPmPnMSlea2s02DkSASARG/edit?usp=sharing&ouid=106912853763388518804&rtpof=true&sd=true https://drive.google.com/drive/folders/1DOWE3Rc2dH6C-VPlGSmbm9ZdGs3koF-Q?usp=sharing |  |  |  |  |
| ### 1.3 Bi-Weekly and Monthly Psychosocial Support Meetings | Regular bi-weekly and monthly VSG meetings were conducted to strengthen psychosocial wellbeing, emotional resilience, and survivor preparedness for engagement in TJ processes. Sessions focused on trauma coping strategies, peer support, personal safety planning, survivor rights, and referral pathways. Across the implementation period, these meetings recorded over 2,800 cumulative participations, reflecting sustained survivor engagement rather than unique individuals. Women consistently accounted for approximately 60% of participants. - Direct beneficiaries: 2,800+ participations (approx. 60% women) - Indirect beneficiaries: Community members reached through survivor peer networks Photo link: https://docs.google.com/document/d/1LVKugwLCx16DUX2b9brCmQ7nyQ0EThC/edit?usp=sharing&ouid=106912853763388518804&rtpof=true&sd=true https://docs.google.com/document/d/1LVKugwLCx16DUX2b9brCmQ7nyQ0EThC/edit?usp=sharing&ouid=106912853763388518804&rtpof=true&sd=true https://docs.google.com/document/d/1aTgvyADsyVSxfz9tywphMKmogosvxStG/edit?usp=sharing&ouid=106912853763388518804&rtpof=true&sd=true https://drive.google.com/drive/folders/1VD8vHs8ZgcvLxNG1RaXXYLBQ6tadCvIt?usp=sharing |  |  |  |  |
| ### 1.4 Community Dialogue Sessions | I-WIN facilitated structured community dialogue sessions to promote collective understanding of Transitional Justice, truth-telling, reparations, reconciliation, and the mandate of the CTRH. Dialogues were conducted in local languages using trauma-sensitive approaches to ensure safe and meaningful participation. - Direct beneficiaries: 120 participants (approx. 70 women) - Indirect beneficiaries: ~600 community members (approx. 60% women) Photo link: https://docs.google.com/document/d/1P7_E6ekGbwn4zPBgQofDJcNeIrjzWuYP/edit?usp=sharing&ouid=106912853763388518804&rtpof=true&sd=true https://docs.google.com/document/d/1P7_E6ekGbwn4zPBgQofDJcNeIrjzWuYP/edit?usp=sharing&ouid=106912853763388518804&rtpof=true&sd=true |  |  |  |  |
| ### 1.5 Leadership Dialogue and Capacity-Building Sessions | Leadership dialogue sessions and capacity-building trainings were conducted to strengthen the role of traditional leaders, county officials, women and youth leaders, religious leaders, and CSOs in supporting survivor-centred TJ processes. Leaders were equipped with skills on survivor protection, stigma reduction, referrals, restorative justice, and community mobilization. - Direct beneficiaries: 330 leaders engaged; 165 leaders trained (approx. 50% women) - Indirect beneficiaries: ~2,000 community members reached through leader-led sensitisation Photo link: https://docs.google.com/document/d/1BYxsEfwjpKoqaSoqxdU1y9fNVFVmlaH/edit?usp=sharing&ouid=106912853763388518804&rtpof=true&sd=true https://docs.google.com/document/d/19Bqoynhy5_T7gAh3sCvZDoUFEsokRPju/edit?usp=sharing&ouid=106912853763388518804&rtpof=true&sd=true https://docs.google.com/document/d/1aOHd2S0cwyyJccMQjn6x07CWZT6vaU2r/edit?usp=sharing&ouid=106912853763388518804&rtpof=true&sd=true https://drive.google.com/drive/folders/1IvvP5K8j7aJm6kfiSoU5ryxLndhf3ECU?usp=sharing https://drive.google.com/drive/folders/1VCO9M1QmSscPaCSm1HI4qNCov2Es0n9W?usp=sharing |  |  |  |  |
| ### 1.6 Community Outreach Sessions | Targeted outreach sessions were conducted in markets, IDP settlements, and residential areas to expand public awareness of TJ principles, survivor rights, CTRH processes, and available psychosocial and legal support services. Sessions were delivered in simplified formats to reach low-literacy audiences. - Direct beneficiaries: 800+ community members (approx. 480 women) - Indirect beneficiaries: ~3,000 community members (approx. 60% women) Photo link: https://docs.google.com/document/d/11yj2t8j3VyF_wFqjQpppAcZe2M4CMKPO/edit?usp=sharing&ouid=106912853763388518804&rtpof=true&sd=true https://docs.google.com/document/d/1P7_E6ekGbwn4zPBgQofDJcNeIrjzWuYP/edit?usp=sharing&ouid=106912853763388518804&rtpof=true&sd=true https://docs.google.com/document/d/11yj2t8j3VyF_wFqjQpppAcZe2M4CMKPO/edit?usp=sharing&ouid=106912853763388518804&rtpof=true&sd=true https://drive.google.com/drive/folders/1eHCNwozR-1oIBMA3saUmFW77rQv3mtZn?usp=sharing |  |  |  |  |
| ### 1.7 Radio Talk Shows on Transitional Justice | Nine interactive radio talk shows were produced and aired on Kondial FM, reaching communities across Bentiu and neighbouring counties. The programs addressed survivor rights, CTRH mandate, reparations, stigma reduction, and community roles in reconciliation, with active listener engagement through call-ins and SMS. - Direct beneficiaries: 135 studio participants and contributors (approx. 80 women) - Indirect beneficiaries: 14,000+ listeners (approx. 60% women) Media link: https://docs.google.com/document/d/1nEUtBNsToIdVDT5Etv9KGRjnyLTnq_Dn/edit?usp=drive_link&ouid=106912853763388518804&rtpof=true&sd=true ttps://docs.google.com/document/d/1-LVKugwLCx16DUX2b9brCmQ7nyQ0EThC/edit?usp=sharing&ouid=106912853763388518804&rtpof=true&sd=true https://drive.google.com/drive/folders/1D0cgOCxD1tvYHCYAn2d9DVFcer8qAfC6?usp=sharing |  |  |  |  |
| ### 1.8 Drama-Based Community Sensitisation | Drama-based sensitisation activities were implemented to communicate TJ concepts and address SGBV stigma through culturally appropriate storytelling. Performances were followed by facilitated reflection discussions to deepen understanding and empathy. - Direct beneficiaries: 1,400+ participants (approx. 840 women) - Indirect beneficiaries: ~3,500 community members (approx. 60% women) Media link: https://docs.google.com/document/d/1gWHoQvAgjMg67HAhOqpKom1WGSx4u3f/edit?usp=sharing&ouid=106912853763388518804&rtpof=true&sd=true https://www.facebook.com/share/v/1BvZA1hFnV/ https://www.facebook.com/share/v/1D8Rtx515S/ https://drive.google.com/file/d/1RTNYZsEud3IF31Lq8r2VD6MmYAwcdzaI/view?usp=sharing https://docs.google.com/document/d/1NJolDAoaWqeD_MJBKV3lExEKQrPyvfVA/edit?usp=sharing&ouid=106912853763388518804&rtpof=true&sd=true https://drive.google.com/drive/folders/1eURhrFq8If3TfV1x3Ce135gwwuCZd2zi?usp=sharing |  |  |  |  |
| - Please describe the major outcomes and differences made from your activities as part of this project in the period under review |  |  |  |  |  |
| During the period under review, the interventions implemented by Invisible Women Inclusion Network (I-WIN) delivered substantial, measurable, and transformative outcomes that meaningfully advanced survivor-centred transitional justice in Rubkona County and Bentiu IDP Camp, Unity State. The project generated individual, community, institutional, and systemic changes, moving transitional justice from a largely abstract concept to a practical, locally owned, and survivor-driven process, closely aligned with emerging national mechanisms, particularly the Commission for Truth, Reconciliation and Healing (CTRH). |  |  |  |  |  |
| ### 2.1 Strengthened Survivor Participation, Agency, and Leadership | A core outcome of the project was the significant strengthening of survivor participation and voice, especially among women and survivors of sexual and gender-based violence (SGBV). Through the establishment and strengthening of 50 Victim Support Groups (VSGs), more than 700 conflict-affected survivors directly engaged in structured, safe, and survivor-led platforms. Approximately 65% of these survivors were women and girls, many of whom had previously been excluded from public dialogue, justice-related processes, and community decision-making. Survivors transitioned from silence and isolation to active participation, demonstrating increased confidence to discuss their experiences, engage in collective reflection, and contribute to conversations on truth-telling, reparations, reconciliation, and non-recurrence. Women survivors, in particular, experienced a notable shift from passive participation to visible leadership roles, including VSG facilitators, peer counsellors, record keepers, and community mobilizers. This represents a qualitative change in survivor agency, positioning survivors not merely as beneficiaries but as active actors shaping transitional justice processes at community level. |  |  |  |  |
| ### 2.2 Improved Psychosocial Wellbeing and Survivor Resilience | The project achieved strong psychosocial outcomes through sustained, trauma-informed engagement embedded within VSG activities. Over the course of implementation, more than 2,800 cumulative participations were recorded in bi-weekly and monthly VSG meetings, indicating high levels of trust, relevance, and continued survivor engagement rather than one-off attendance. Survivors reported reduced emotional distress, improved coping mechanisms, stronger peer support networks, and increased self-esteem. Many survivors—particularly women affected by SGBV—shared experiences openly for the first time in safe settings, demonstrating enhanced emotional resilience and readiness to engage in dialogue and reconciliation processes. Importantly, survivors requiring specialized assistance were identified early and supported through functional referral pathways, with over 36 survivors accessing medical, psychosocial, or legal services, including Clinical Rape Management (CRM). This integration of psychosocial care strengthened survivor safety and ensured that participation in transitional justice processes did not lead to re-traumatization. |  |  |  |  |
| ### 2.3 Increased Community Awareness and Ownership of Transitional Justice | Another major outcome was the substantial improvement in community awareness, understanding, and acceptance of transitional justice. Through a layered approach combining community dialogues, leadership engagements, outreach sessions, radio talk shows, and drama-based sensitisation, the project directly reached over 6,000 individuals and indirectly reached more than 15,000 community members, with women constituting over 60% of those reached. Communities demonstrated improved understanding of the multiple pillars of transitional justice—truth-seeking, reparations, accountability, reconciliation, and guarantees of non-recurrence—and increasingly recognized the relevance of these processes to everyday experiences of loss, displacement, and harm. Transitional justice is now more widely understood as a collective and community-driven process, rather than a distant, elite-led, or purely legal intervention. This shift in perception is critical to the long-term legitimacy and effectiveness of national transitional justice mechanisms. |  |  |  |  |
| ### 2.4 Reduced Stigma and Positive Behavioural Change | The project contributed to a measurable reduction in stigma toward survivors, particularly women affected by SGBV, persons with disabilities, and children born of conflict. Drama-based sensitisation, survivor testimonies, and facilitated community dialogues humanized survivor experiences and challenged harmful norms of blame, silence, and exclusion. Communities demonstrated positive behavioural changes, including increased acceptance of survivor participation in public forums, improved family and peer support, and greater respect for women survivors as contributors to peace and reconciliation. Survivors reported feeling safer to speak publicly and to participate in VSGs and community dialogues. These shifts created more enabling social environments for disclosure, healing, and sustained engagement in justice and reconciliation processes. |  |  |  |  |
| ### 2.5 Strengthened Leadership Accountability and Institutional Engagement | Leadership dialogue sessions and capacity-building trainings strengthened the role of community and county-level leaders in supporting survivor-centred transitional justice. A total of 165 leaders—including traditional chiefs, women leaders, youth leaders, religious leaders, county officials, and civil society representatives—were directly trained, with women representing approximately 50% of participants. Leaders demonstrated increased understanding of survivor protection, confidentiality, stigma reduction, and referral mechanisms. Many leaders began integrating transitional justice messaging into routine community meetings, customary structures, and dispute-resolution forums, reflecting a shift from ad hoc engagement to institutionalized support for survivor-centred approaches. Through leader-led mobilisation, an estimated 2,000 additional community members were reached indirectly, further reinforcing community ownership and sustainability. |  |  |  |  |
| ### 2.6 Strengthened Linkages Between Community and National Transitional Justice Processes | A critical systemic outcome was the strengthening of linkages between grassroots survivor initiatives and national transitional justice processes. Survivors gained clearer understanding of the mandate, scope, and limitations of the CTRH and were better prepared to engage safely and meaningfully when opportunities arise. Notably, at least 15 women VSG leaders transitioned from community-based participation to involvement in national-level transitional justice consultations facilitated by civil society coalitions and partners. This represents an important advancement in ensuring women’s survivor voices inform national transitional justice planning, helping to bridge the gap between local experiences and national policy processes. Radio talk shows further amplified community narratives beyond local contexts, contributing to wider public discourse on survivor rights and transitional justice. |  |  |  |  |
| ### Overall Difference Made | Overall, the project produced a durable shift from survivor marginalization, stigma, and silence toward organized survivor participation, empowered leadership, informed community engagement, and stronger community-to-national linkages. Transitional justice in the project areas is now grounded in survivor experiences, supported by accountable leadership, and sustained through community-owned structures. These outcomes represent a significant and lasting contribution to inclusive, survivor-centred transitional justice in Unity State and provide a strong foundation for effective engagement with the Commission for Truth, Reconciliation and Healing in South Sudan. |  |  |  |  |
| - What were the key lessons learned (if any) from the project in the period under review |  |  |  |  |  |
| Implementation of the project during the period under review yielded critical strategic, programmatic, and operational lessons for survivor-centred transitional justice programming in fragile and post-conflict contexts such as Unity State. These lessons are derived from sustained engagement with survivors, community structures, leadership actors, and institutional stakeholders, and they provide actionable insights to inform future transitional justice initiatives supported by ATJLF and other partners. |  |  |  |  |  |
| ### 3.1 Survivor-Centred and Trauma-Informed Programming Is a Non-Negotiable Foundation | A central lesson from the project is that meaningful survivor participation cannot occur without deliberate, sustained attention to emotional safety, dignity, and trust. Survivors—particularly women affected by sexual and gender-based violence (SGBV)—were willing to participate consistently only when activities were rooted in trauma-informed principles, including voluntariness, confidentiality, informed consent, respect, and controlled pacing. Practical approaches such as women-only safe spaces, gradual storytelling, clear group agreements, grounding techniques, and survivor choice regarding disclosure significantly reduced fear, stigma, and risks of re-traumatisation. Where these safeguards were firmly applied, survivors moved beyond attendance to sustained engagement and leadership. Where they were less applied, participation remained cautious and limited. This underscores the lesson that survivor-centred design is not an added value but an ethical and operational prerequisite for transitional justice work. |  |  |  |  |
| ### 3.2 Survivor Leadership and Local Ownership Are the Primary Drivers of Sustainability | The project demonstrated that local ownership—especially survivor leadership—is the strongest determinant of sustainability. Victim Support Groups (VSGs) became more resilient and effective as survivor leaders gradually assumed responsibility for facilitation, peer counselling, mobilisation, and coordination. Survivors displayed higher trust and openness when discussions were led by individuals with shared lived experiences and cultural familiarity. Early investment in leadership capacity building—covering facilitation skills, safeguarding, referral pathways, and transitional justice concepts—enabled survivor leaders and community actors to progressively reduce reliance on external facilitation. This transition created a sense of ownership and accountability that is likely to sustain activities beyond the project lifecycle, reinforcing the lesson that sustainability is built during implementation, not at project closure. |  |  |  |  |
| ### 3.3 Transitional Justice Understanding Requires Time, Repetition, and Multi-Layered Engagement | The project reinforced the lesson that transitional justice concepts cannot be effectively communicated through one-off or short-term sensitisation activities. Complex ideas such as truth-seeking, reparations, non-recurrence, and accountability require time, repetition, and contextualisation to be understood and embraced. Regular VSG meetings, iterative community and leadership dialogues, outreach sessions, radio programmes, and drama-based sensitisation allowed communities to progressively move from confusion, scepticism, or unrealistic expectations toward clearer understanding and informed engagement. Repeated exposure across different platforms proved essential for correcting misinformation, managing expectations, and embedding transitional justice within everyday community discourse. |  |  |  |  |
| ### 3.4 Creative, Context-Appropriate Communication Significantly Enhances Reach and Impact | Another key lesson was the effectiveness of creative and culturally relevant communication tools in low-literacy and displacement settings. Radio talk shows expanded outreach beyond physical meeting spaces, reaching women, IDPs, and remote populations who face structural barriers to participation. Drama-based sensitisation translated complex transitional justice concepts into emotionally resonant narratives that elicited empathy, reflection, and open discussion. These methods proved more effective than technical explanations alone in challenging stigma, normalising survivor voices, and stimulating spontaneous community dialogue. The lesson highlights the importance of integrating non-traditional, people-centred communication approaches into transitional justice programming to maximise reach and behavioural change. |  |  |  |  |
| ### 3.5 Clear Expectation Management Is Essential to Maintain Trust and Engagement | The project highlighted the importance of continuous expectation management in transitional justice interventions. Many survivors initially associated justice initiatives with material or humanitarian assistance. Where expectations were not addressed early and clearly, confusion and frustration risked undermining trust. Transparent and repeated communication about the project’s objectives, scope, and limitations—combined with effective referral pathways to existing service providers—helped maintain credibility and participation. This lesson confirms that expectation management is not a one-time activity but an ongoing process critical to sustaining survivor trust and engagement. |  |  |  |  |
| ### 3.6 Inclusion Requires Deliberate Design, Resourcing, and Monitoring | The project demonstrated that meaningful inclusion of women, persons with disabilities, youth, IDPs, returnees, and elderly survivors does not occur automatically. Inclusion must be intentionally planned, resourced, and monitored. Accessible venues, flexible scheduling, adapted facilitation techniques, peer support mechanisms, and leadership opportunities were necessary to move from symbolic inclusion to genuine participation. Deliberate inclusion enhanced the quality of dialogue, strengthened survivor voices, reduced power imbalances, and increased the legitimacy of community-led transitional justice processes. This lesson underscores that equity and inclusion require active investment at every stage of project design and implementation. |  |  |  |  |
| ### 3.7 Integrating Psychosocial Support Strengthens Justice Outcomes | A further lesson was that psychosocial healing and transitional justice processes are mutually reinforcing. Survivors who received consistent psychosocial support were better prepared to engage in dialogue, documentation, leadership roles, and reconciliation efforts. Emotional stability and peer support enhanced survivors’ ability to articulate experiences safely and to participate without harm. Conversely, justice processes that are disconnected from psychosocial support risk exclusion and re-traumatisation. Integrating psychosocial care within transitional justice programming strengthened survivor resilience, improved participation quality, and enhanced the sustainability of outcomes. |  |  |  |  |
| ### 3.8 Structured Community-to-National Linkages Increase Legitimacy of Transitional Justice | The project also demonstrated that intentional preparation of survivors and leaders for engagement with national transitional justice mechanisms is essential. Community-based engagement alone is insufficient unless structured pathways exist to link grassroots experiences to national processes. Supporting survivor documentation, leadership mediation, and participation in national consultations enabled community voices—particularly women’s voices—to inform emerging CTRH processes. This lesson highlights the importance of building vertical linkages between community-level initiatives and national transitional justice institutions to enhance legitimacy, inclusiveness, and effectiveness. |  |  |  |  |
| ### Overall Learning | Overall, the project confirmed that survivor-centred transitional justice is most effective when it is emotionally safe, locally led, sustained over time, creatively communicated, clearly framed, psychosocially integrated, intentionally inclusive, and linked to national processes. These lessons have strengthened I-WIN’s institutional capacity and will directly inform future programming, advocacy, and engagement with the Commission for Truth, Reconciliation and Healing in South Sudan, as well as contribute to ATJLF’s broader learning and replication objectives. |  |  |  |  |
| 4 |  |  |  |  |  |
| - Describe the challenges experienced during the course of this project in the period under review and how you dealt with them. |  |  |  |  |  |
| During the period under review (August 2025 – April 2026), the project was implemented within a complex post-conflict and humanitarian context in Rubkona County and Bentiu IDP Camp. While the project achieved its objectives, several contextual, operational, and psychosocial challenges were encountered. These were proactively addressed through adaptive management, strong community engagement, and trauma-informed approaches. Limited Initial Understanding of Transitional Justice. Many community members and survivors initially had limited awareness of transitional justice concepts and, at times, expected material or humanitarian assistance rather than process-oriented justice, healing, and reconciliation. This was addressed through intensified, repeated sensitisation using community dialogues, outreach sessions, radio talk shows, and simplified messaging delivered in local languages. Clear communication on the scope and limitations of the project helped align expectations, while referral pathways were used to link survivors to relevant service providers where appropriate. Stigma, Fear, and Emotional Distress among Survivors. Survivors—particularly women affected by sexual and gender-based violence (SGBV)—experienced fear, stigma, and emotional distress that initially limited participation. I-WIN mitigated this through trauma-informed facilitation, establishment of women-only safe spaces, clear confidentiality protocols, and deployment of trained psychosocial facilitators. Survivors requiring specialised care were referred to medical, psychosocial, or legal services through strengthened referral mechanisms. Mobility, Accessibility, and Weather-Related Constraints. Seasonal flooding, poor road conditions, and mobility challenges—especially for persons with disabilities, elderly survivors, and women with caregiving responsibilities—affected attendance in some locations. These constraints were addressed by decentralising activities, relocating meetings closer to communities, adjusting schedules, and engaging community volunteers to support vulnerable participants. Security and Camp-Related Operational Constraints. Occasional localized insecurity and shifting dynamics within the IDP camp posed operational risks. I-WIN maintained close coordination with local authorities and UNMISS, adopted flexible scheduling, and applied risk-informed planning to ensure participant and staff safety. Low Literacy Levels. Low literacy among some participants constrained comprehension of complex TJ concepts. This was mitigated through the use of visual aids, drama-based sensitisation, oral facilitation, and interactive discussion methods. Overall, adaptive implementation, strong community trust, and continuous risk mitigation enabled the project to manage challenges effectively while safeguarding survivor participation, dignity, and project quality. |  |  |  |  |  |
| - BENEFICAIRIES OF ACTION: Elaborate the number of people reached in the implementation of the action in the period under review: Disaggregate based on AGE and Gender i.e. Number of women, victims and young people reached, number of people reached and sensitized about TJ and TJ frameworks, number of people reached through the media and other awareness raising efforts etc. (Provide documents to support the number as indicated in the Log frame). You can provide answer in a table. |  |  |  |  |  |
| During the period under review, the project reached a substantial number of direct and indirect beneficiaries through survivor-centred Transitional Justice (TJ) interventions implemented in Rubkona County and Bentiu IDP Camp, Unity State. Beneficiary data were collected using attendance registers, monitoring tools, referral logs, radio station records, and partner reports, and were disaggregated by gender, age group, and beneficiary category, in line with the approved Logframe and MEAL framework. ### A. Direct Beneficiaries (Disaggregated by Gender and Age) Activity / Beneficiary Category; Adult Men; Adult Women; Youth (18–30); Total Direct Beneficiaries; Remarks. Official Project Launch; 20; 30; –; 50; Government, UN, CSOs, women & youth leaders. Victim Support Groups (VSGs) – Membership; 245; 455; Included; 700+; Survivors of SGBV, IDPs, returnees, PWDs, elderly survivors. Bi-Weekly & Monthly VSG Meetings*; 1,120; 1,680; Included; 2,800+; Cumulative participations across 16 bi-weekly & 9 monthly meetings. Community Dialogue Sessions; 50; 70; Included; 120; Survivors, women leaders, elders, religious leaders. Leadership Dialogue Sessions; 145; 185; Included; 330; Chiefs, county officials, women & youth leaders. Leadership Capacity-Building Trainings; 82; 83; Included; 165; VSG leaders & community leaders. Community Outreach Sessions; 320; 480; Included; 800+; Markets, IDP camps, residential areas. Drama-Based Sensitisation (Direct Audience); 560; 840; Included; 1,400+; Public performances on TJ & SGBV stigma. Radio Talk Shows – Studio Participants; 55; 80; Included; 135+; Moderators, guests, survivors, experts. Referrals to Medical, Legal & Psychosocial Services; 14; 22; –; 36+; CRM, counselling & legal aid. * Note: Participation figures reflect repeat attendance by active survivors and should not be interpreted as unique individuals. B. Indirect Beneficiaries (Estimated Reach) Channel / Activity; Estimated Indirect Reach; Women & Girls (%); Remarks. VSG Peer-to-Peer & Household Dissemination; 6,500; 60%; Information sharing by VSG members. Community Dialogue Follow-Up Mobilisation; 600; 60%; Cascaded awareness at household & block level. Leadership-Led Sensitisation; 2,000; 60%; Messaging by chiefs & religious leaders. Community Outreach Follow-Up; 3,000; 60%; Peer dissemination & informal discussions. Drama-Based Sensitisation (Ripple Effect); 3,500; 60%; Community word-of-mouth & youth engagement. Radio Talk Shows (Kondial FM); 14,000+; 60%; Listeners across 7 counties in Unity State. |
| - ASSESSMENT OF THE OVERALL PROJECT |  |  |  |  |  |
| - Have the overall objectives of the project been achieved? if yes, please state how. if not, please say why not. |  |  |  |  |  |
| The project successfully met its core objectives of strengthening survivor participation—particularly women survivors of sexual and gender-based violence (SGBV)—in Truth, Justice, Reconciliation and Accountability processes; enhancing community understanding of transitional justice (TJ); and building community and leadership readiness for engagement with the Commission for Truth, Reconciliation and Healing (CTRH). This was achieved through the establishment and strengthening of 50 functional Victim Support Groups (VSGs) across Rubkona County and Bentiu IDP Camp, which directly engaged 1000+ conflict-affected survivors, with 60–65% women and girls. The VSGs provided safe, survivor-led platforms for psychosocial support, peer counselling, documentation of violations, and preparation for truth-telling and reconciliation, enabling survivors to transition from silence and isolation to organised participation and leadership. The project also significantly increased community awareness and acceptance of transitional justice, reaching over 6,000 individuals directly and 15,000+ indirectly through layered sensitisation approaches, including community and leadership dialogues, outreach sessions, drama-based sensitisation, and nine interactive radio talk shows. Communities demonstrated improved understanding of TJ principles, reduced stigma—particularly around SGBV—and increased willingness to support survivor participation. In addition, the project strengthened local leadership capacity and accountability, training 165 leaders (50% women) and engaging 330 leaders through dialogue sessions. Leaders increasingly integrated survivor-centred TJ messaging into community forums and supported referrals and reconciliation initiatives. Importantly, the project also laid foundations for national-level engagement, with at least 15 women survivor leaders progressing from community-based participation to engagement in national transitional justice consultations linked to CTRH preparatory processes. Overall, by meeting or exceeding planned targets and delivering sustained changes in survivor agency, community awareness, leadership engagement, and community-to-national linkages, the project successfully achieved its stated objectives. |  |  |  |  |  |
| - Please summarize all project activities implemented in the last twelve months. |  |  |  |  |  |
| Over the last 9 months, the project implemented by Invisible Women Inclusion Network (I-WIN) delivered a comprehensive package of survivor-centred, community-based, and leadership-focused activities aimed at strengthening participation in Truth, Justice, Reconciliation and Accountability processes in Rubkona County and Bentiu IDP Camp, Unity State. Implementation followed a phased and integrated approach, moving from foundation-building to consolidation and community ownership. Project launch and stakeholder engagement. The project was officially launched in August 2025 through a multi-stakeholder event that brought together government authorities, UN agencies, civil society organisations, traditional and religious leaders, women and youth representatives, persons with disabilities, IDPs, and returnees. This activity established shared understanding of project objectives, clarified transitional justice concepts and the mandate of the Commission for Truth, Reconciliation and Healing (CTRH), and secured early buy-in and coordination among key actors. Establishment and strengthening of Victim Support Groups (VSGs). The project established and strengthened 50 Victim Support Groups across Bentiu IDP Camp and surrounding communities. These groups became the primary grassroots platforms for survivor participation, psychosocial support, peer counselling, truth-telling preparation, stigma reduction, and collective advocacy for justice and reparations. Survivors participated voluntarily under safeguarding and confidentiality principles, with deliberate prioritisation of women and other vulnerable groups. Bi-weekly and monthly VSG meetings (psychosocial support). Regular bi-weekly and monthly VSG meetings were conducted throughout the year to strengthen psychosocial wellbeing, emotional resilience, and survivor preparedness for transitional justice engagement. Sessions focused on trauma awareness, coping strategies, trust-building, personal safety planning, survivor rights, stigma reduction, and referral pathways. These meetings ensured continuity of survivor engagement and sustained healing processes. Capacity-building trainings for VSG leaders and community leaders. Structured capacity-building trainings were delivered for VSG leaders, traditional leaders, women leaders, youth leaders, religious leaders, and civil society actors. Training modules covered transitional justice principles and the CTRH mandate, trauma-informed and ethical facilitation, survivor protection, referral mechanisms, restorative justice, reparations, mediation, and leadership skills. These trainings strengthened local ownership and enabled leaders to independently support survivor-centred activities. Community dialogue sessions. The project conducted structured community dialogue sessions in selected locations to promote open, inclusive discussions on transitional justice, truth-telling, reconciliation, reparations, and non-recurrence. Dialogues were facilitated in local languages using participatory and trauma-sensitive methods, enabling survivors and community members to jointly reflect on past harms, justice needs, and pathways toward healing and coexistence. Leadership dialogue sessions. Dedicated leadership dialogue sessions were organised to strengthen the accountability and role of local leaders in supporting survivor participation and reconciliation. These sessions deepened leaders’ understanding of transitional justice and promoted commitments to survivor protection, stigma reduction, referrals, and integration of TJ principles into community governance and customary structures. Community outreach activities. Targeted community outreach sessions were conducted in markets, IDP settlements, and residential areas to extend awareness beyond organised forums. Outreach activities used simplified, accessible messaging to reach low-literacy and hard-to-reach groups, focusing on survivors’ rights, the CTRH, available support services, and the importance of community participation in reconciliation and healing. Radio talk shows on transitional justice. Nine interactive radio talk shows were produced and aired on Kondial FM, significantly expanding outreach across Unity State. The programmes featured I-WIN staff, partner institutions, community leaders, and survivor representatives, and addressed transitional justice principles, survivor rights, stigma, reparations, and the CTRH. Call-ins and SMS engagement enabled real-time community interaction. Drama-based community sensitization. Drama-based sensitisation activities were implemented as a culturally appropriate tool to communicate transitional justice concepts, address stigma—particularly related to SGBV—and foster empathy and dialogue. Performances were followed by facilitated reflections that encouraged community discussion and collective learning. Monitoring, Evaluation, Accountability and Learning (MEAL). MEAL was implemented as a cross-cutting activity throughout the 9 months, including routine monitoring, data collection, beneficiary feedback, learning reviews, and adaptive management. This ensured accountability to beneficiaries, evidence-based decision-making, and alignment with the approved logframe. Together, these activities formed an integrated and mutually reinforcing intervention package that strengthened survivor agency, community awareness, leadership engagement, and preparedness for meaningful participation in transitional justice processes at both community and national levels. |  |  |  |  |  |
| - Please Summarize all key project achievements for the last 12 months. Include relevant numbers for each achievement. E.g. The project successfully trained 200 journalists on a module (specify name of training module). |  |  |  |  |  |
| Over the last 9 months, the project implemented by Invisible Women Inclusion Network (I-WIN) achieved the following key results, in line with the approved logframe: - 50 Victim Support Groups (VSGs) established and strengthened across Rubkona County and Bentiu IDP Camp. - 1000+ survivors directly engaged through VSG membership, with 60–65% women and girls, including survivors of SGBV, IDPs, returnees, persons with disabilities, youth, and elderly survivors. - 2,800+ cumulative participations recorded through 16 bi-weekly and 9 monthly VSG meetings, indicating sustained survivor engagement and trust. - 165 leaders (50% women) trained on transitional justice principles, CTRH mandate, trauma-informed facilitation, ethical storytelling, referrals, reparations, and mediation. - 330 community and county leaders engaged through leadership dialogue sessions, strengthening accountability and local ownership. - 120 individuals participated in structured community dialogue sessions on truth-telling, reconciliation, and non-recurrence. - 800+ community members reached directly through targeted community outreach activities (approximately 60% women). - 1,400+ participants reached through drama-based sensitisation, addressing SGBV stigma and survivor dignity. - Nine (9) interactive radio talk shows aired on Kondial FM, reaching 14,000+ listeners across Unity State. - 30+ studio participants and contributors engaged in radio programs, with over 100 call-ins and SMS interactions recorded. - 36+ survivors successfully referred for medical, legal, and psychosocial services, including Clinical Rape Management (CRM). - 15 women survivor leaders are ready from community-based participation to national-level transitional justice consultations linked to CTRH preparatory processes. - 6,000+ individuals reached directly and 15,000+ community members reached indirectly through outreach, media, leadership mobilisation, and peer dissemination. Overall, these achievements demonstrate that the project met and, in several areas, exceeded its planned targets by strengthening survivor participation, expanding community awareness of transitional justice, reducing stigma, building accountable leadership, and laying strong foundations for meaningful engagement with national transitional justice mechanisms in South Sudan. |  |  |  |  |  |
| - Overall, what worked well in the implementation of the project. |  |  |  |  |  |
| Several elements worked particularly well in the implementation of the project and were central to achieving the intended results. Strong survivor-centred and trauma-informed approach. The consistent application of survivor-centred and trauma-informed principles proved highly effective. Creating safe, confidential spaces through Victim Support Groups (VSGs) enabled survivors—especially women affected by sexual and gender-based violence (SGBV)—to participate voluntarily, build trust, and engage meaningfully without fear of re-traumatisation. This approach led to high retention, sustained participation, and the emergence of survivor leadership. Community ownership and local leadership engagement. Early and continuous engagement of traditional leaders, women leaders, youth leaders, religious leaders, and local authorities strengthened legitimacy and acceptance of the project. Leadership dialogues and capacity-building ensured that transitional justice messaging was reinforced through existing community and customary structures, promoting sustainability beyond the project lifecycle. Effective use of layered communication and outreach strategies. The combination of community dialogues, outreach sessions, drama-based sensitisation, and radio talk shows worked well in reaching diverse audiences, including low-literacy groups, IDPs, and remote communities. Radio programming and drama proved especially effective in simplifying complex transitional justice concepts, addressing stigma, and expanding reach beyond physical gatherings. Strong focus on capacity building and sustainability. Training VSG leaders and community leaders enabled a gradual shift from externally facilitated activities to locally led processes. By the end of implementation, trained leaders were independently facilitating meetings, referrals, and sensitisation, demonstrating effective skills transfer and strong local ownership. Adaptive and flexible implementation. The project team responded well to contextual challenges such as mobility constraints, weather disruptions, and security considerations by decentralising activities, adjusting schedules, and maintaining close coordination with local authorities and UNMISS. This flexibility ensured continuity of activities and safety of participants. Robust coordination and partnerships. Collaboration with government institutions, UN agencies, civil society actors, and community structures worked well and enhanced coordination, referrals, and credibility. These partnerships strengthened the project’s reach and effectiveness while reinforcing alignment with national transitional justice efforts. Effective Monitoring, Evaluation, Accountability and Learning (MEAL). The MEAL system supported evidence-based decision-making, regular reflection, and adaptive management. Continuous monitoring and beneficiary feedback mechanisms ensured accountability, improved activity quality, and documented measurable results. Overall, the combination of survivor-centred design, strong community ownership, inclusive communication approaches, effective partnerships, and adaptive implementation contributed significantly to the project’s success. |  |  |  |  |  |
| - What do you think could have worked better and what did you wish you had done differently for those things to work better? |  |  |  |  |  |
| While the project was successfully implemented and achieved its core objectives, reflective assessment highlighted several areas that could have worked better and informed lessons on what might be done differently in future programming. Earlier and deeper community sensitisation on transitional justice concepts. Although awareness improved substantially over time, some initial misunderstandings persisted around transitional justice, with expectations of material or humanitarian assistance. In retrospect, a longer inception phase with more intensive early-stage sensitisation—especially using simplified messaging and community influencers—could have reduced confusion and managed expectations from the outset. Stronger integration of psychosocial expertise from the start. The demand for psychosocial support was higher than initially projected, particularly among women survivors of SGBV. While referral pathways functioned well, integrating a greater number of trained psychosocial facilitators earlier in the project would have strengthened survivor support and reduced the response burden during peak periods of participation. More systematic age-disaggregated data collection. Although gender disaggregation was consistently applied, age-specific tracking—particularly for youth—was not always captured in sufficient detail across activities. Introducing more robust age-disaggregated monitoring tools from the beginning would have strengthened analysis of youth participation and tailored programming more effectively to younger survivors and community members. Earlier linkage between survivor empowerment and livelihoods support. Economic vulnerability repeatedly emerged as an underlying barrier to sustained participation, especially for women survivors. While not within the project’s mandate, earlier coordination with livelihood actors or complementary income-generating initiatives could have enhanced survivor resilience and long-term engagement. Expanded engagement with schools and youth structures. Youth participated actively, but engagement with formal and informal youth platforms could have been broadened to deepen intergenerational dialogue on justice, memory, and reconciliation. Overall, if additional time and resources had permitted, earlier investment in expectation management, psychosocial capacity, age-sensitive monitoring, and livelihood linkages would have further strengthened outcomes. These reflections will directly inform the design and sequencing of future survivor-centred transitional justice interventions. |  |  |  |  |  |
| - What was the beneficiaries’ perception of your project? |  |  |  |  |  |
| Overall, beneficiaries’ perception of the project was highly positive, with many describing it as relevant, empowering, safe, and transformative. Feedback collected through VSG meetings, community dialogues, outreach sessions, and informal discussions consistently indicated strong appreciation for the project’s survivor-centred and inclusive approach. Survivors’ perspectives. Survivors—particularly women affected by sexual and gender-based violence (SGBV)—perceived the project as a rare and trusted platform that restored dignity and provided emotional safety. Many beneficiaries reported that the Victim Support Groups (VSGs) were the first spaces where they felt able to speak openly, be listened to without judgment, and receive peer support. Survivors valued the voluntary and confidential nature of participation and expressed increased confidence, self-worth, and readiness to engage in truth-telling and reconciliation discussions. Women beneficiaries frequently noted feeling “seen,” “respected,” and “empowered” through the project. Community perceptions. At community level, beneficiaries increasingly perceived the project as legitimate, inclusive, and responsive to local realities. Community members appreciated the use of accessible communication methods—such as drama and radio—which helped demystify transitional justice concepts and encouraged open discussion. Many reported improved understanding of survivor rights and reduced stigma toward survivors, particularly women and children born of conflict. The project was widely viewed as contributing to healing, coexistence, and social cohesion. Leaders’ and stakeholders’ views. Traditional leaders, religious leaders, and local authorities perceived the project as constructive and complementary to community peace efforts. They valued the capacity-building and dialogue components, noting that these strengthened their ability to support survivors, address stigma, and integrate transitional justice messages into community forums. Leaders increasingly regarded survivor participation as legitimate and necessary for sustainable peace. Overall perception. Across beneficiary groups, the project was perceived not merely as an awareness initiative, but as a meaningful process that enabled healing, voice, and collective responsibility. Beneficiaries expressed trust in the project team and a strong desire for the continuation and scaling-up of similar survivor-centred transitional justice interventions. |  |  |  |  |  |
| - What difference ATJLF funding has made to transitional justice in your country? |  |  |  |  |  |
| ATJLF funding has made a significant, tangible, and lasting contribution to advancing survivor-centred transitional justice in South Sudan, particularly in Unity State. The support moved transitional justice from a largely abstract national agenda into a practical, community-owned process grounded in survivor experiences, dignity, and participation. From exclusion to survivor agency: Prior to ATJLF support, survivors—especially women affected by sexual and gender-based violence (SGBV), IDPs, persons with disabilities, and returnees—had limited safe spaces to engage in justice discussions and little confidence that their voices mattered. ATJLF funding enabled the establishment and strengthening of Victim Support Groups (VSGs) as sustainable grassroots platforms where survivors could heal, organise, and participate meaningfully. As a result, hundreds of survivors transitioned from silence and isolation to confidence, leadership, and collective action in truth-telling, reconciliation, and accountability processes. Strengthening women’s voices and leadership: A distinct difference made by ATJLF funding is the amplification of women’s survivor voices. Women now constitute the majority of active participants and leaders within community-based transitional justice structures. Several women survivor leaders progressed from community-level engagement to participation in national transitional justice consultations linked to the Commission for Truth, Reconciliation and Healing (CTRH), ensuring that grassroots female perspectives inform national justice processes—something previously rare in South Sudan. Building community understanding and reducing stigma: ATJLF funding enabled wide-scale community sensitisation through dialogues, outreach, radio programming, and drama-based approaches. Transitional justice is now increasingly understood as a collective, community-driven responsibility rather than a distant, elite-led or purely legal process. Stigma toward survivors—particularly SGBV survivors and children born of conflict—has measurably declined, creating safer environments for disclosure, healing, and participation. Strengthening leadership accountability and local ownership: Through capacity-building and leadership dialogues supported by ATJLF, traditional leaders, religious leaders, women leaders, and local authorities now play more active roles in survivor protection, referrals, and reconciliation. Transitional justice principles are increasingly integrated into customary and community governance structures, strengthening sustainability beyond project funding. Bridging community and national transitional justice processes: Crucially, ATJLF funding helped bridge the long-standing gap between grassroots survivors and national transitional justice mechanisms. Communities are now better prepared, informed, and organised to engage with the CTRH, enhancing the legitimacy, inclusiveness, and future effectiveness of national processes. Overall difference made: In summary, ATJLF funding catalysed a durable shift in South Sudan from stigma to dignity, exclusion to participation, and fragmentation to community-driven reconciliation. By centring survivor voices and empowering communities, the Fund has laid a strong foundation for inclusive, legitimate, and sustainable transitional justice in the country. |  |  |  |  |  |
| - How has this project contributed in bringing about change in the problem you had identified in your proposal? |  |  |  |  |  |
| The project has made a direct and measurable contribution to addressing the core problem identified in the proposal: the systematic exclusion of survivors—particularly women survivors of sexual and gender-based violence (SGBV)—from transitional justice processes, compounded by stigma, trauma, weak community awareness, and limited connection to national justice mechanisms. Addressing survivor exclusion and silence: At the outset, survivors lacked safe spaces to speak, organise, and participate meaningfully in Truth, Justice, Reconciliation and Accountability processes. Through the establishment and strengthening of 50 Victim Support Groups (VSGs), the project created trusted, survivor-led platforms where survivors could engage voluntarily, heal psychosocially, and prepare for truth-telling. This directly transformed survivor participation from isolation and silence to structured, collective engagement. Reducing stigma and fear: Stigma—especially toward women affected by SGBV—was a major barrier identified in the proposal. The project addressed this through layered community sensitisation, including dialogues, outreach, radio talk shows, and drama-based approaches. These activities challenged harmful norms, increased empathy, and normalised survivor voices. As a result, communities became more accepting of survivor participation, creating safer environments for disclosure and engagement. Strengthening survivor capacity and confidence: Trauma, lack of confidence, and limited understanding of rights previously prevented survivors from engaging in justice processes. By integrating trauma-informed psychosocial support, peer counselling, and capacity-building within VSGs, the project enabled survivors—particularly women—to rebuild self-confidence, assume leadership roles, and engage in public dialogue on justice and reconciliation. Increasing community understanding of transitional justice: The proposal identified low awareness and misconceptions about transitional justice as a key obstacle. The project significantly improved understanding of TJ principles and the mandate of the Commission for Truth, Reconciliation and Healing (CTRH) by reaching thousands through accessible, locally appropriate communication channels. Transitional justice is now increasingly understood as a community-relevant and survivor-centred process, rather than a distant or elite-driven agenda. Bridging community and national processes: A critical gap identified in the proposal was the disconnect between grassroots survivors and national transitional justice mechanisms. The project addressed this by preparing survivors and leaders for engagement with national processes. Notably, women survivor leaders progressed from community participation to national-level consultations, ensuring that grassroots perspectives now inform CTRH preparatory discussions. Overall contribution to change: Collectively, the project shifted the problem from exclusion, stigma, and fragmentation toward organised survivor agency, informed community ownership, accountable leadership, and strengthened links to national transitional justice processes. Transitional justice in the project areas is no longer abstract or inaccessible, but rooted in survivor experiences and sustained through community-owned structures—demonstrating a fundamental change from the conditions described in the original proposal. |  |  |  |  |  |
| - How does your organization intend to leverage on the results of this project in its future work? |  |  |  |  |  |
| Invisible Women Inclusion Network (I-WIN) intends to strategically leverage the results, structures, lessons, and partnerships generated through this project to deepen, expand, and sustain survivor-centred transitional justice interventions in South Sudan. The project has significantly strengthened I-WIN’s institutional capacity, community credibility, and evidence base, which will directly inform and shape future programming. Scaling and sustaining Victim Support Groups (VSGs): I-WIN will build on the success of the 50 established Victim Support Groups (VSGs) by supporting their continued operation as long-term community platforms for healing, truth-telling preparation, survivor advocacy, and referrals. Trained VSG leaders will be positioned as local facilitators and multipliers, enabling expansion of the model to additional counties and IDP settings while reducing dependence on external facilitation. Strengthening survivor leadership and women’s participation: The project generated a strong cohort of women and survivor leaders with practical experience in facilitation, dialogue, and advocacy. I-WIN will continue mentoring these leaders and strategically support their engagement in state- and national-level transitional justice processes, including consultations linked to the Commission for Truth, Reconciliation and Healing (CTRH). Survivor leadership development will remain a core pillar of future programs. Deepening community-to-national transitional justice linkages: Lessons and pathways established through this project will be used to strengthen vertical linkages between grassroots survivors and national transitional justice institutions. I-WIN will leverage survivor documentation, community insights, and leadership networks generated under the project to contribute evidence-based inputs into CTRH planning, policy dialogue, and advocacy efforts. Integrating psychosocial support into justice programming: Recognising the strong complementarity between healing and justice, I-WIN will continue to integrate trauma-informed psychosocial support into all future transitional justice and peacebuilding initiatives. Referral systems and partnerships strengthened through the project will be sustained and expanded to ensure survivor safety and wellbeing. Informing program design and fundraising: The project’s documented outcomes, beneficiary stories, and MEAL evidence will be used to inform the design of future proposals, attract complementary funding, and advocate for longer-term, survivor-centred transitional justice investments—particularly those addressing women’s leadership and economic vulnerability. Knowledge sharing and institutional learning: Finally, I-WIN will use the learning generated to contribute to national and regional knowledge-sharing platforms, peer learning forums, and policy discussions on transitional justice in Africa, ensuring that grassroots South Sudanese survivor experiences inform broader practice. In summary, I-WIN will leverage the results of this project to scale impact, sustain survivor agency, strengthen national engagement, and institutionalise survivor-centred transitional justice approaches across its future work. |  |  |  |  |  |
| - ASSESSMENT OF THE RELATIONSHIP WITH THE ATJLF |  |  |  |  |  |
| - What suggestions (if any) do you have for the ATJLF secretariat if it intends to replicate your project in other countries? |  |  |  |  |  |
| Based on extensive implementation experience, monitoring data, and direct engagement with survivors and communities, Invisible Women Inclusion Network (I-WIN) offers the following technical and programmatic recommendations to guide ATJLF if it intends to replicate this project model in other country contexts. a) Institutionalise survivor-led community structures as the foundation of replication: Replication efforts should be anchored in survivor-led and survivor-owned community platforms, such as Victim Support Groups (VSGs), from the earliest stages of implementation. These structures proved essential for building trust, sustaining participation, reducing stigma, and enabling survivors—particularly women and SGBV survivors—to move from passive recipients to active agents of transitional justice. ATJLF should ensure that replication budgets and designs explicitly support the formation, mentorship, and long-term functioning of such grassroots survivor structures. b) Embed trauma-informed psychosocial support as a non-negotiable pillar: The project demonstrated that survivor participation in transitional justice is inseparable from psychosocial safety and healing. Replication should therefore integrate trauma-informed approaches across all activities, including trained facilitators, clear safeguarding protocols, confidential referral pathways, and partnerships with psychosocial and medical service providers. Without this integration, survivor engagement risks being superficial, ethically problematic, or harmful. c) Adopt phased, multi-stage implementation timelines: Transitional justice interventions require time, repetition, and trust-building to produce meaningful change. Replication should avoid short or compressed timelines and instead adopt phased programming that allows communities to progress gradually from awareness-raising, to survivor empowerment, to leadership ownership, and finally to structured engagement with national transitional justice mechanisms. Longer-term funding windows will significantly enhance depth, quality, and sustainability of outcomes. d) Promote contextualised and inclusive communication strategies: The project confirmed that multi-modal, culturally appropriate communication tools—including community dialogues, radio programming, and drama-based sensitisation—are highly effective, particularly in low-literacy, displacement, and post-conflict settings. Replication efforts should invest in locally adapted communication methods, use local languages, and prioritise formats that resonate with women, youth, and marginalised groups, rather than relying solely on technical or legal messaging. e) Strengthen deliberate linkages between community-level and national TJ processes: Replication should intentionally prepare survivors and local leaders to engage with national transitional justice mechanisms. This includes providing clear information about mandates, managing expectations, strengthening survivor documentation practices, and facilitating ethical pathways for representation in national consultations. Such linkages enhance both the legitimacy of national mechanisms and the relevance of community participation. f) Invest in strong MEAL systems focused on learning and accountability to survivors: Replication across countries will benefit from robust Monitoring, Evaluation, Accountability and Learning (MEAL) frameworks that capture not only outputs but also qualitative change, survivor perceptions, and social norms shifts. Feedback mechanisms that allow survivors to shape programming in real time should be standard practice. Overall Recommendation: For replication to be effective, ATJLF should maintain flexibility, context sensitivity, survivor leadership, adequate timeframes, and strong protection standards. Replicated projects should prioritise depth of engagement over speed, ensuring that transitional justice interventions are ethically grounded, locally owned, and capable of producing durable social and institutional change across diverse country contexts. |  |  |  |  |  |
| - What is your assessment of the collaboration with the ATJLF? Did you receive adequate support from the ATJLF throughout the implementation of your project? Please explain. |  |  |  |  |  |
| Invisible Women Inclusion Network (I-WIN) assesses its collaboration with the Africa Transitional Justice Legacy Fund (ATJLF) as strong, constructive, and highly supportive throughout the entire project lifecycle. Overall, ATJLF provided adequate and timely support that enabled effective implementation, adaptive management, and achievement of intended results. Strategic and programmatic support: From project inception, the ATJLF Secretariat demonstrated a clear understanding of survivor-centred transitional justice and the complex operating environment in South Sudan. The Secretariat provided strategic guidance that helped align project activities with ATJLF priorities and broader transitional justice frameworks, particularly regarding survivor participation, gender responsiveness, and ethical engagement. This strategic alignment strengthened the project’s focus and relevance. Responsive communication and accessibility: Communication with ATJLF was open, respectful, and responsive. The Secretariat maintained regular communication channels and was accessible for clarification, guidance, and feedback. Queries related to reporting, implementation adjustments, or contextual challenges were addressed promptly, enabling the project team to make informed decisions without disrupting implementation timelines. Flexibility and adaptive management: ATJLF demonstrated flexibility and understanding of the fluid and challenging context in Unity State, including displacement dynamics, seasonal flooding, and security considerations. Where minor adjustments were required in timelines or activity sequencing, the Secretariat was receptive and supportive, allowing I-WIN to adapt implementation while remaining aligned with agreed objectives and budgetary frameworks. Support for accountability, learning, and reporting: The guidance provided on narrative reporting, logframe alignment, and documentation of outcomes strengthened I-WIN’s Monitoring, Evaluation, Accountability and Learning (MEAL) practices. ATJLF’s emphasis on honest reflection, learning, and evidence-based reporting encouraged continuous improvement rather than purely compliance-driven reporting. Respect for local leadership and ownership: Importantly, ATJLF consistently respected and trusted I-WIN’s contextual knowledge and grassroots expertise. This approach allowed the organisation to exercise local leadership, build strong community relationships, and maintain survivor trust—an essential condition for effective transitional justice programming. Overall assessment: In summary, ATJLF provided adequate financial, technical, and relational support throughout the project. The collaboration was characterised by mutual trust, professionalism, flexibility, and a shared commitment to survivor-centred justice. This supportive partnership significantly contributed to the project’s success and set a strong foundation for future collaboration. |  |  |  |  |  |
| - How has the ATJLF funding supported the sustainability of your organisation and your interventions? Explain in detail how ATJLF’s funding has supported your viability and sustainability as an organisation. |  |  |  |  |  |
| ATJLF funding has played a critical and strategic role in strengthening the institutional viability, programmatic sustainability, and long-term impact of Invisible Women Inclusion Network (I-WIN). Beyond supporting time-bound activities, the funding enabled I-WIN to build enduring systems, capacities, and partnerships that will continue to advance survivor-centred transitional justice beyond the project period. Strengthening organisational credibility and positioning: ATJLF’s support significantly enhanced I-WIN’s credibility at community, state, and national levels. Successful implementation of a high-impact, survivor-centred transitional justice project positioned I-WIN as a trusted and competent actor in transitional justice, survivor support, and gender-responsive peacebuilding in South Sudan. This strengthened reputation has improved I-WIN’s visibility with government institutions, UN agencies, civil society partners, and donors, expanding opportunities for collaboration and future funding. Building durable community structures for sustained impact: ATJLF funding enabled the establishment and strengthening of 50 Victim Support Groups (VSGs) as community-owned platforms for survivor healing, peer support, and justice engagement. These VSGs are not dependent on continuous external funding for basic functioning. Trained survivor leaders and facilitators can sustain meetings, referrals, and awareness activities, ensuring continuity of impact beyond the grant period and reducing long-term programmatic costs. Investing in human capital and leadership capacity: Through supported capacity-building initiatives, ATJLF funding strengthened the skills of I-WIN staff, VSG leaders, and community leaders in trauma-informed facilitation, transitional justice, safeguarding, referrals, mediation, and leadership. This investment in human capital has increased internal institutional capacity, reduced reliance on external consultants, and enhanced I-WIN’s ability to design, implement, and manage complex transitional justice programs sustainably. Institutionalising survivor-centred systems and approaches: The funding allowed I-WIN to refine and institutionalise survivor-centred, trauma-informed programming methodologies, safeguarding protocols, referral systems, and participatory accountability mechanisms. These systems are now embedded within I-WIN’s organisational practices and will be applied across future projects, ensuring consistent quality, ethical standards, and survivor protection. Strengthening partnerships and resource leveraging: ATJLF funding facilitated durable partnerships with local authorities, UNMISS, service providers, community structures, and national civil society networks. These partnerships enhance sustainability by enabling cost-sharing, referrals, coordinated advocacy, and technical support beyond the lifespan of the grant. Evidence and outcomes generated through the project are also being used to leverage additional funding and complementary support. Enhancing organisational learning, MEAL, and fundraising capacity: The strong emphasis on Monitoring, Evaluation, Accountability and Learning (MEAL) supported by ATJLF strengthened I-WIN’s ability to document results, generate credible evidence, and articulate impact. These capacities directly support organisational sustainability by improving proposal quality, donor confidence, learning-driven adaptation, and strategic planning. Overall sustainability contribution: In sum, ATJLF funding supported I-WIN not only to deliver project outputs, but to build an organisation that is more resilient, credible, professionally equipped, and strategically positioned to sustain and scale survivor-centred transitional justice interventions. The funding has laid a foundation for long-term institutional viability and ensured that the project’s benefits continue through empowered survivors, functioning community structures, and strengthened organisational systems. |  |  |  |  |  |
| - What other recommendations (if any) do you have for the ATJLF? |  |  |  |  |  |
| Building on the positive collaboration and results achieved through this project, Invisible Women Inclusion Network (I-WIN) respectfully offers the following additional recommendations to further strengthen ATJLF’s effectiveness, learning role, and long-term impact across its portfolio: a) Support longer-term and flexible funding windows: Given that transitional justice processes require time, trust-building, and iterative engagement, ATJLF may consider providing longer funding cycles or phased extensions for well-performing projects. This would enable grantees to consolidate gains, support sustainability, and deepen community-to-national linkages without disruption. b) Institutionalise cross-country learning and peer exchange: ATJLF could add value by creating structured peer-learning platforms (e.g., annual convenings, thematic learning circles, or virtual exchanges) where grantees share tools, challenges, survivor-centred methodologies, and lessons across countries. This would strengthen collective knowledge and innovation within the Fund’s network. c) Provide light-touch technical accompaniment: In addition to financial support, ATJLF may consider offering optional technical accompaniment—such as advisory clinics on safeguarding, survivor representation, advocacy, or MEAL for social norm change—to help grantees strengthen quality and consistency while retaining local ownership. d) Strengthen communication and visibility of survivor-centred impact: ATJLF could further amplify impact by supporting ethical, survivor-safe documentation and storytelling guidelines, common visibility standards, and curated impact products that highlight survivor voices and grantee achievements at continental and global levels. e) Encourage strategic linkages between community and policy levels: ATJLF may continue to incentivise projects that explicitly bridge grassroots survivor initiatives with national and regional transitional justice frameworks, including support for safe survivor participation in policy dialogue and TJ institution-building. f) Continue prioritising learning-oriented accountability: Finally, I-WIN encourages ATJLF to maintain its emphasis on learning-focused reporting and honest reflection, ensuring that both successes and challenges inform adaptive programming and strengthen the Fund’s long-term strategic impact. Overall, these recommendations are intended to complement ATJLF’s strong existing approach and to further enhance its role as a learning, survivor-centred, and transformative fund for transitional justice in Africa. |  |  |  |  |  |
| - ASSESSMENT OF THE RELATIONSHIP WITH OTHER ATJLF GRANTEES AND LOCAL AUTHORITIES |  |  |  |  |  |
| - Did you collaborate with other ATJLF grantees during the implementation of this project? If yes, what was the nature of the engagement? If no, please explain why. |  |  |  |  |  |
| During the implementation of this project, Invisible Women Inclusion Network (I-WIN) did not engage in direct, structured collaboration with other ATJLF grantees on joint activities. This was primarily due to the context-specific and geographically focused nature of the project, which concentrated on survivor-centred transitional justice interventions in Rubkona County and Bentiu IDP Camp, Unity State. Other ATJLF-supported initiatives were implemented in different locations or addressed distinct thematic priorities, limiting opportunities for direct operational collaboration. However, while formal joint programming did not take place, informal and indirect engagement occurred at learning and coordination levels. I-WIN participated in ATJLF-convened spaces, reporting processes, and knowledge-sharing opportunities, which allowed for the exchange of experiences, approaches, and lessons with other grantees. These interactions supported cross-learning on survivor-centred methodologies, community engagement strategies, safeguarding practices, and outcomes documentation, even in the absence of shared field activities. The absence of direct collaboration was therefore not due to lack of willingness or openness, but rather to practical considerations related to geography, timelines, and project scope. I-WIN remains open and committed to deeper collaboration with other ATJLF grantees in future programming—particularly through structured peer-learning platforms, joint advocacy initiatives, or cross-regional survivor representation efforts—should alignment in context and timing allow. Overall, while collaboration with other ATJLF grantees during this project was limited to informal knowledge exchange, the relationship contributed positively to learning and reflective practice across the ATJLF grantee community. |  |  |  |  |  |
| - What was your level of collaboration (if any) with other TJ stakeholders and local authorities in your country as it pertains to the implementation of this project? Please describe the nature of the engagement. (300 max) |  |  |  |  |  |
| Invisible Women Inclusion Network (I-WIN) maintained a high and constructive level of collaboration with transitional justice (TJ) stakeholders and local authorities throughout the implementation of this project. This collaboration was central to the project’s effectiveness, legitimacy, and sustainability, particularly given the sensitive nature of survivor-centred transitional justice work in a post-conflict setting. Collaboration with local and state authorities: I-WIN worked closely with county and payam authorities in Rubkona County, block leaders in Bentiu IDP Camp, and relevant state-level institutions, including the Relief and Rehabilitation Commission (RRC). Local authorities were engaged from the project launch stage and throughout implementation to facilitate community entry, mobilisation, security coordination, and alignment with existing governance structures. Their involvement enhanced community trust, supported survivor protection, and reduced resistance to sensitive topics such as SGBV, truth-telling, and stigma. Engagement with traditional and religious leaders: Traditional chiefs, elders, and religious leaders were key partners, particularly in community and leadership dialogue sessions. Their participation helped bridge customary practices with transitional justice principles and reinforced anti-stigma, reconciliation, and survivor-protection messages within communities. Coordination with TJ and human rights stakeholders: I-WIN collaborated with TJ-relevant actors, including UNMISS (Human Rights Division), psychosocial service providers, legal aid actors, and civil society organisations working on peacebuilding, gender, and justice. These partnerships strengthened referral pathways for survivors, enriched dialogue facilitation, and ensured accurate and survivor-centred messaging on the Commission for Truth, Reconciliation and Healing (CTRH). Nature and value of engagement: Collaboration took the form of joint dialogues, participation in radio programs, referral coordination, technical input, and advisory support. Stakeholders also contributed to learning, contextual analysis, and alignment with national TJ developments. Overall, collaboration with TJ stakeholders and local authorities was strong, continuous, and mutually reinforcing, significantly enhancing project relevance, survivor safety, community ownership, and readiness for engagement with national transitional justice processes. |  |  |  |  |  |

| Use this space to share at least three beneficial testimonials to highlight the project’s impact (1000 words max). Please include the names and photos of the concerned beneficiaries. The photos should be shared using a Google Drive link or as attachments to the email. |
| --- |
| The following testimonials illustrate the tangible impact of the project on survivors, community leaders, and grassroots participants in Rubkona County and Bentiu IDP Camp. All testimonials were collected with informed consent, respecting dignity, confidentiality, and ethical storytelling standards. Photos of beneficiaries will be shared separately via Google Drive links or as email attachments, in line with ATJLF visibility guidelines. ### Testimonial 1: Survivor Empowerment and Healing through Victim Support Groups Name: Nyaluak Deng Age: 34 Location: Bentiu IDP Camp Profile: Survivor of conflict-related sexual violence; Victim Support Group (VSG) member and peer supporter “Before joining the Victim Support Group, I lived with fear and shame. I never spoke about what happened to me—not even to my family. I thought my pain was something I deserved to hide.” Nyaluak joined a Victim Support Group established by I-WIN during the early phase of the project. Through regular bi-weekly and monthly meetings, trauma-informed facilitation, and peer support, she began to rebuild confidence and emotional resilience. “In the group, I saw other women like me. I learned that what happened was not my fault. Slowly, I found my voice.” Over time, Nyaluak transitioned from silent participation to becoming a peer supporter within her VSG. She now supports newly enrolled survivors and actively participates in community dialogues. “Today, I help other women speak. When someone is quiet, I sit with her and tell her, ‘You are not alone.’ This project gave me strength and dignity.” Nyaluak’s journey reflects the project’s impact in transforming survivors from isolation to leadership, and from trauma to meaningful participation in transitional justice processes. ### Testimonial 2: Community Attitude Change and Leadership Accountability Name: Chief Bol Gatluak Age: 52 Location: Rubkona County Profile: Traditional community leader and leadership dialogue participant “In the past, we did not understand transitional justice. We believed survivors should stay silent for the sake of peace.” Chief Bol participated in leadership dialogue sessions organised under the project. Through these dialogues, he gained a clearer understanding of survivor dignity, trauma, and the role of community leaders in reconciliation. “The trainings helped me see that silence does not heal wounds. Justice and healing must include survivors, especially women.” Following the dialogues, Chief Bol committed to integrating survivor-centred messaging into community meetings and dispute resolution forums. He has since encouraged survivors to join Victim Support Groups and spoken publicly against stigma related to sexual and gender-based violence. “Now, in my community meetings, I tell people that survivors deserve respect, not blame. This project changed how leaders think and act.” His testimony highlights how the project strengthened leadership accountability and shifted community norms toward empathy, inclusion, and reconciliation. ### Testimonial 3: Youth and Community Awareness through Drama and Radio Name: Rebecca Nyabang Age: 22 Location: Pakur Area, Rubkona County Profile: Youth participant; drama sensitisation audience member “Before the drama performance, I only heard rumors about transitional justice. I did not know it was about healing and truth.” Rebecca attended a drama-based community sensitisation session organised by I-WIN. The performance addressed stigma, survivor dignity, and the role of the Commission for Truth, Reconciliation and Healing (CTRH). “The drama showed how survivors suffer when communities blame them. It touched my heart.” After the drama session and subsequent discussion, Rebecca began sharing information learned with her peers and family members. “I now talk to my friends about respecting survivors and supporting peace. Even at home, my parents listen when I explain what I learned.” Rebecca later tuned into radio talk shows broadcast on Kondial FM and encouraged other young people to listen. “Radio helped us understand more. This project opened our minds and taught us that justice belongs to everyone.” Her testimony demonstrates the project’s success in increasing awareness among youth and extending impact beyond direct participants ### Summary of Testimonial Impact Collectively, these testimonials demonstrate that the project: - Restored survivor dignity, confidence, and leadership, particularly among women; - Enabled community and traditional leaders to actively support survivor-centred justice; - Reached youth and wider communities through creative and accessible sensitisation approaches; - Contributed to reduced stigma, improved dialogue, and stronger foundations for reconciliation. |  |