PROJECT IMPLEMENTATION REPORT #1

Project Title: Sustainable Livelihoods and Empowerment of Women Returnees in Magwi County through the Pass-on-the-Gift Goat Initiative

Implementing Agency: Invisible Women Inclusive Network (I-WIN) Project

Location: Pajok Payam, Magwi County, South Sudan

Project Duration: 10 Months Reporting Period: 31 January 2026 – 03 February 2026

Donor: African Women for Change Network (AfNet)

- Executive Summary

This report summarizes the first phase of the Pass-on-the-Gift Goat Initiative, targeting 20 vulnerable women returnees in Pajok Payam, Magwi County. Key outcomes include: - Beneficiary engagement: 20 women identified, including widows, GBV survivors, women with disabilities, and households with no livestock. - Livestock distribution: 40 goats procured and handed over, with veterinary inspection, vaccination, and deworming completed. - Capacity building: Beneficiaries trained in husbandry, veterinary care, record keeping, and socio-economic skills. - Community structures established: 10-member Community Livelihood Oversight Committee (CLOC) and 20-member Women Livestock Solidarity Group (WLSG) to oversee project sustainability.

Challenges included scarcity of goats, limited technical capacity of local veterinary officers, and limited availability of local authorities. The project is positioned for scaling up to additional Bomas and Payams based on high community interest and observed impact.

- Project Overview

The initiative applies a community-driven, asset-transfer livelihood restoration model using the Pass-on-the-Gift methodology. This model ensures: - Beneficiary ownership and accountability - Long-term sustainability of livestock assets - Expansion of benefits through offspring transfer to additional vulnerable women

The project addresses critical vulnerabilities among women returnees in Pajok Payam, promoting income generation, improved nutrition, and community resilience.

- Methodology and Community Engagement

Community Entry and Stakeholder Engagement: - Government: RRC, County Agriculture Department, Payam Agriculture Extension Worker, Payam Veterinary Officer, Payam Administrator - Traditional leaders: Executive Chief, Boma Chiefs of Chaigon, Lagi, Pajok, and Lawaci - Community representatives: Religious leaders, youth leaders, women representatives, opinion leaders

Beneficiary Identification: Conducted jointly with Boma Chiefs using validated vulnerability screening tools.

Livestock Distribution: Conducted at Boma headquarters under supervision of Payam Agriculture Extension Worker, Veterinary Officer, and Boma Chiefs.

- Implementation Activities, Achievements, and Next Steps

Table 1: Planned Activities, Achievements, and Next Steps

| Activity | Achievements | Next Steps |
| --- | --- | --- |
| Community entry & validation | Formal meetings with authorities and community leaders to establish legitimacy | Quarterly review meetings with RRC and Payam authorities |
| Beneficiary mobilization & contracting | 20 beneficiaries selected prioritizing widows, GBV survivors, women with disabilities, returnees, livestock-less households | Profile socio-economic status; identify next 20 beneficiaries for expansion |
| Livestock procurement & distribution | 40 goats procured aftermarket assessment; all underwent veterinary inspection, vaccination, deworming | Establish monthly veterinary check-ups; implement procurement protocols for future transfers |
| Capacity building & technical training | Training delivered in: Husbandry (feeding, shelter, breeding cycles); Veterinary care (early disease detection, CAHW support); Record keeping & financial management; Socio-economic skills (household planning, milk utilization) | Conduct follow-up site visits; coordinate FAO and County/State Agriculture support |
| Monitoring & peer accountability | 10-member CLOC and 20-member WLSG established; CAHWs trained in monitoring & reporting | Facilitate monthly WLSG meetings; maintain CLOC oversight |
| Asset transfer / handover | 40 goats distributed (1 male & 1 female per beneficiary); formal contracts signed for Pass-on-the-Gift | Initiate tracking ledger to monitor goat pregnancies and offspring transfer |
| Pass-on execution & sustainability | Local committees ensure ongoing oversight and accountability | Identify and pre-validate secondary beneficiaries for offspring transfer |

- Project Indicators and Targets

| Indicator | Baseline | Target | Achievement to Date |
| --- | --- | --- | --- |
| Number of women receiving goats | 0 | 20 | 20 |
| Number of goats distributed | 0 | 40 | 40 |
| Number of trained beneficiaries | 0 | 20 | 20 |
| Number of community oversight committees established | 0 | 2 | 2 |
| Number of goats passed on to secondary beneficiaries | 0 | 40 | 0 (next cycle) |

- Budget Utilization Summary

| Budget Item | Approved Budget (USD) | Expenditure to Date (USD) | % Utilized |
| --- | --- | --- | --- |
| Livestock procurement | 3,077 | 3,058 | 99% |
| Capacity building & training | 961 | 884 | 92% |
| Monitoring & evaluation | 577 | 462 | 80% |
| Community engagement & logistics | 385 | 366 | 95% |
| Total | 5000 | 4770 | 95% |

- Challenges

- Limited availability of local authorities delayed some activities.

- Goat scarcity in Pajok Payam required alternative sourcing from neighboring Bomas.

- Resource limitations prevented support for all vulnerable women.

- Limited technical capacity of Agriculture Extension Workers and Veterinary Officers led to livestock transfer without formal health certification.

- Lessons Learned and Recommendations

- Early engagement with local authorities is critical to streamline project activities.

- Community-based committees (CLOC, WLSG) are essential for monitoring, accountability, and sustainability.

- Scarcity of livestock highlights the need for alternative procurement strategies and partnerships.

- Scaling up to remaining Bomas and neighboring Payams is recommended based on high interest and potential impact.

- Training and capacity building of local veterinary staff should be integrated into future cycles.

- Conclusion and Transition to Next Cycle

The Input-to-Output phase is complete, with strong community engagement, asset distribution, and capacity building achieved. Authorities and beneficiaries have welcomed the initiative as a pathway to rapid livelihood recovery. Scaling up to additional Bomas in Pajok and neighboring Payams (Obbo, Palwa) is recommended to enhance income, nutrition, and resilience among women returnees.

- Annexes (Optional)

- Annex 1: List of beneficiaries with demographic details

- Annex 2: Training attendance sheets and materials

- Annex 3: Photographs of goat distribution and training sessions

photos

https://drive.google.com/drive/folders/1BZzU_eNaxjqEFW3dzO6zmPxMHAThQ58T?usp=sharing

photo document

https://drive.google.com/drive/folders/1HeGHbpc-3zYWFH7QCAWlopLA2ctnjvmn?usp=sharing

videos

https://drive.google.com/drive/folders/10CoNVgsNfCcO6ncK0iVtGKSRx4XVS9ok?usp=sharing

- Annex 4: Signed Pass-on-the-Gift contracts

- Annex 5: Pass-on tracking ledger template

Prepared by: Invisible Women Inclusive Network (I-WIN) Date: 03 February 2026