Appendix 1: Project planning –

basis for monitoring and evaluation

| Organisation: | Invisible Women Inclusion Network (I-WIN) | Date of submission: | 21.10.2025 |
| --- | --- | --- | --- |
| Project title: | Youth at the Helm – Mediation and Reconciliation for Crisis Prevention in Bor South County | Date of revised version: | 17.04.2026 |
| Project duration: | 01.05.2026 – 31.12.2026 |  |  |

Impact - Describe your concrete vision of the future: Given the current situation described in the analysis (Application form, topic 4.), what are the long lasting changes to which the project will contribute? - How will you be able to assess those changes?

a) Impact The project envisions a peaceful and resilient Greater Jonglei, where communities resolve disputes through inclusive dialogue rather than violence. Over the long term, youth (14-35) and women will occupy formal roles in community peace structures, leading to a 20% reduction in inter-communal clashes and enhanced inter-ethnic cooperation across Bor South County, including displaced communities from northern Jonglei now residing in Bor South. - Assessment of long-lasting change: - UNMISS and Protection Cluster incident data (before/after comparison). - Qualitative testimonies from community leaders, mediators, and women’s groups. - County government recognition of peace committees as permanent conflict-resolution mechanisms.

| Key actors within the project | Outcome | Milestones (Process indicators) |
| --- | --- | --- |
| Identify individuals or groups that you intend to work with for the purpose of facilitating the desired changes. Please explain the criteria and procedures used when selecting participants, especially aspects of group affiliation (e.g. gender, religion, ethnicity, age, region of origin, sexual orientation) | How do the actions of the key actors change so that the desired changes can occur? | On the way to achieve the outcomes, which process indicators (milestones) can manifest that the key actors are acting differently? Based on which means and sources can you assess the achievement of the milestones (e.g. questionnaire, observations by project implementing the project, interviews with project participants and with others)? |
| Key actor 1: Youth Mediators (80 people, 50 % women) Selection criteria: - Must be between 14–35 years old and resident in Bor South County (including displaced youth from northern Jonglei counties now residing in Bor South). - Demonstrated respect within their community (nominated by chiefs, women’s leaders, or faith-based representatives). - Represents major ethnic groups (Dinka, Nuer, Murle) with balanced participation. - Minimum literacy sufficient to complete mediation forms; preference for those with secondary education or prior leadership roles. - Commitment to neutrality, gender equality, and non-violence principles. | Youth mediators will acquire practical skills in mediation, trauma-healing, and dialogue facilitation, transforming from potential conflict actors into peace advocates. They will become visible agents of change, initiating local reconciliation processes, mentoring peers, and leading youth forums. Over time, trained mediators will be recognised by local authorities as community peace resources-actively resolving conflicts, calming tensions, and bridging divides between ethnic youth groups. This shift will contribute directly to preventing small disputes from escalating into revenge attacks or wider violence. | Milestones: - 80 youth mediators trained through two 5-day sessions on mediation and trauma-healing. - At least 70 % of trainees actively engaged in local dispute resolution. - Minimum 25 conflicts mediated successfully by youth-led initiatives. - Formation of a “Youth Mediation Network” for experience sharing. Means / sources for the assessment of the milestones: - Training attendance and pre/post-tests. - Mentorship logs and reflection meeting reports. - Documentation of mediated cases, success stories, and committee reports. - Feedback from chiefs and local leaders confirming effectiveness. |
| #### Key actor 2: Peace Committees (6 inter-ethnic, gender-balanced groups) Selection criteria: - Formed across six payams in Bor South County (one per major payam). - Members (10 per committee) nominated jointly by chiefs, women’s associations, youth groups, and church leaders to ensure inclusivity. - Composition: 5 men and 5 women; at least 2 members aged under 30. - Representation from all local ethnic and clan groups to ensure legitimacy. - Members must be permanent residents, respected, and without political affiliation or record of violence. | The committees will become trusted and permanent local mechanisms for early warning, mediation, and reconciliation. They will serve as the first responders to emerging tensions and coordinate with county peace offices and UNMISS. Their authority is to be strengthened through signed peace agreements and regular meetings that will track violations and promote adherence to local pacts. As committees gain legitimacy, they will institutionalise participatory, gender-balanced decision-making in peace processes and set a model for neighbouring counties. | Milestones: - 6 functional peace committees established with documented membership. - Monthly meetings held with attendance ≥ 80 %. - 2 inter-communal peace agreements negotiated and signed in total for the entire project and the 6 committees - Early-warning alerts submitted quarterly to county authorities. Means / sources for the assessment of the milestones: - Committee meeting minutes and attendance logs. - Copies of peace agreements and MoUs with local government. Reports from UNMISS and Protection Cluster confirming reduced incidents. |
| ### Key actor 3: Community members (1,000 direct participants) Selection Criteria: - Residents of Bor South County, including displaced populations from northern Jonglei and host communities. - Balanced participation of ethnic groups (Dinka, Nuer, Murle). - Gender representation: at least 40 % women per dialogue event. - Inclusion of vulnerable groups; returnees, widows, persons with disabilities, and youth previously associated with armed groups. - Participants selected through local leaders, churches, and existing peace groups. | Communities to shift attitudes from mistrust and retaliation to coexistence and collaboration. Dialogue participants to develop shared understandings of local grievances and commit to non-violent conflict resolution. Inter-ethnic relationships are to be rebuilt through joint cultural, sports, and community initiatives. Women and youth voices to become integral to decision-making in village peace meetings. | Milestones: - 10 inclusive community dialogue forums conducted across Bor South County. - At least 60 % of participants report improved inter-ethnic trust (survey-based). - Community members initiate at least five joint social or livelihood projects. Means / sources for the assessment of the milestones: - Attendance lists, photos, and outcome-harvesting reports. - Pre- and post-dialogue perception surveys. - Observation reports from facilitators and county peace officers. |
| ### Key actor 4: Local Leaders and County Authorities (30 chiefs, administrators, and clergy) Selection Criteria: - Traditional chiefs, women’s chiefs, county commissioners, church leaders, and peace office directors. - Represent both genders and all major ethnic groups. - Hold formal or customary authority recognised by community members. - Demonstrated willingness to support youth and women’s participation in peace structures. | Local leaders and authorities to publicly endorse youth and women-led peace processes and embed these structures into local governance frameworks. They are to provide moral legitimacy and logistical support for peace committees, act as signatories to local peace agreements, and collaborate in monitoring and enforcing them. Their involvement is to create continuity between community peace structures and formal government systems, ensuring sustainability beyond project closure. | Milestones: - Five leadership roundtables convened and MoUs signed with Bor South County authorities. (The MoUs are between the county authorities (County Peace Desks/County Commissioners) and the inter-ethnic peace committees, formally recognising the committees as legitimate local peace actors and outlining their collaboration, roles, and reporting channels) - Chiefs and administrators actively participate in dialogue forums. - County peace offices incorporate committee reports into their annual plans. Means / sources for the assessment of the milestones: - Signed MoUs and local government circulars. - Media coverage and joint communiqués. - Meeting reports from roundtables and evaluation interviews. |
| ### Key actor 5: General Public (150,000 listeners through radio and peace caravans) Selection Criteria: - Residents within broadcast radius of Jonglei and Upper Nile FM stations. - Inclusive of remote pastoralist communities, women, youth, and returnees. - No prior literacy or education requirement; radio programmes produced in Dinka, Nuer, and Murle languages to ensure accessibility | The broader population to gain awareness of peace agreements, understand the benefits of coexistence, and become more tolerant towards other ethnic groups. Radio dramas, music, and interactive call-in shows to foster positive narratives about reconciliation, youth leadership, and women’s participation. The mobile peace caravan is to engage isolated communities through theatre, sports, and storytelling, spreading non-violent communication models. This mass awareness will reinforce behavioural change promoted by mediators and committees, contributing to a culture of peace. | Milestones: - Eight radio programmes and 3 podcasts broadcast across Bor South County. - Three peace caravans reach 15 priority villages and IDP sites. - ≥ 150,000 listeners reached and ≥ 60 % recall peace messages (listener surveys). Means / sources for the assessment of the milestones: - Radio station logs and listener feedback reports. - Social media engagement analytics. - Field monitoring and documentation of caravan events. |

Link Outcome  Impact

- How can the key actors of the project gain influence over the central actors in the context of the crisis / in the context of the democratisation process (according to the focus chosen in your Application form, page 1)? - As a result, how will the actions of the central actors change?

a) The project’s key actors-youth mediators, peace committees, women leaders, community members, and local authorities; will gain influence over central actors through three interlinked mechanisms of engagement, legitimacy, and communication. - Grassroots legitimacy and representation: Trained youth mediators and gender-balanced peace committees will emerge as trusted community representatives. Their local legitimacy will allow them to translate community grievances into structured recommendations, which they will present to chiefs, county commissioners, and the State Ministry of Peacebuilding during dialogue platforms and roundtable forums. Because they will embody the voices of diverse ethnic groups, their perspectives will carry moral weight and political relevance. - Institutionalised collaboration: By signing Memoranda of Understanding (MoUs) with county administrations, peace committees will become part of the official local peace architecture. Through regular reporting to the County Peace Desks and UNMISS Civil Affairs, they will gain institutional visibility and advisory capacity. Their early-warning bulletins and mediation outcomes will influence how local governments prioritise security deployment, response planning, and peace messaging. - Strategic communication and Public opinion influence: The mobile peace caravans and local-language radio programmes reaching over 150,000 citizens, will shape community narratives around coexistence and inclusion. As positive stories of youth-led mediation and women’s leadership circulate, public pressure and social endorsement will compel chiefs and administrators to adopt similar participatory approaches. The combined influence of structured advocacy (committees), consistent information flows (radio and caravans), and local success stories will create a bottom-up accountability dynamic that will reshape the behaviour of power holders. b) As grassroots structures gain visibility and demonstrate results, central actors; county commissioners, state peace ministries, and traditional authorities, will adjust both policy and practice to align with inclusive, community-led peace models. The expected behavioural and institutional changes include: - Integration of Community Peace structures into Formal Governance: County peace offices and traditional councils will adopt the established peace committees as official community-level advisory bodies, ensuring that youth and women are permanently represented in peace planning and conflict-resolution mechanisms. - Adoption of Early-Warning and Response mechanisms: Local governments will begin to rely on the committees’ monthly incident reports for planning deployments and coordinating humanitarian response, creating an evidence-based decision-making culture. - Policy and Normative shift towards inclusion: Chiefs and administrators will begin to invite women and youth to regular peace consultations and public forums, reversing exclusionary norms. These changes will institutionalise gender equality and inter-generational participation, reinforcing South Sudan’s commitments under UNSCR 1325 and 2250. - Replication and Scale-up: The State Ministry of Peacebuilding and UNMISS Peacebuilding Fund will replicate the model in neighbouring counties, acknowledging the approach as a cost-effective and community-driven stabilisation tool. - Sustained Reduction in Localised Violence: As central actors adopt local mechanisms and coordinate more closely with mediators, inter-communal revenge attacks decrease by an estimated 20 %, and previously marginalised groups report improved security perceptions (measured through Protection Cluster and UNMISS indicators).

What concrete contribution should the project make to crisis prevention, stabilisation and peacebuilding / to the democratisation process?

The project “Youth at the Helm – Mediation and Reconciliation for Crisis Prevention in Bor South County” is to contribute directly to crisis prevention and stabilisation by strengthening the local capacities, structures, and relationships necessary for sustainable peace in one of South Sudan’s most conflict-affected regions. Its contribution will operate on three mutually reinforcing levels: community resilience, institutional collaboration, and societal transformation. - Crisis prevention through local mediation and early warning: By training 80 youth mediators and establishing 6 inter-ethnic peace committees, the project will build a grassroots system of conflict anticipation and resolution that will prevent small-scale disputes; such as cattle raids, land disputes, or resource clashes; from escalating into widespread violence. These committees will provide early-warning information to county peace offices, UNMISS, and local authorities, enabling timely interventions. By empowering youth and women to serve as legitimate mediators, the project will reduce recruitment by militias and promotes non-violent dispute resolution pathways. The resulting behavioural shift; where communities resort to negotiation rather than retribution; will directly lower the frequency and severity of inter-communal clashes. In doing so, the project will operationalise the FFO’s emphasis on preventive, subsidiary, and multidimensional peace approaches rooted in local ownership. - Stabilisation through strengthened local governance and inclusive institutions: The project will foster formal recognition and integration of local peace structures into county and state-level governance mechanisms. Through signed Memoranda of Understanding (MoUs) and regular joint review meetings, the committees and mediators will feed structured feedback to local administrators, chiefs, and the State Ministry of Peacebuilding. This integration will achieve two stabilising effects: (1) Rebuild citizen confidence in local authorities by demonstrating responsive governance and accountability to community security concerns. (2) Enhance coordination between communities, chiefs, and security actors, promoting coherence in peacebuilding interventions across Bor South County. Through embedding inclusive participation and gender balance in these local institutions, the project supports state legitimacy and institutional resilience; key pillars of the German Federal Foreign Office’s stabilisation agenda. - Peacebuilding through reconciliation, social cohesion and normative change: At the societal level, the project will promote a culture of peace and reconciliation through 10 dialogue forums, 2 community peace agreements, mobile peace caravans, and radio programming reaching 150,000 people. This extensive outreach will change public narratives from ethnic animosity to coexistence and shared identity. The dialogues and media campaigns will elevate the voices of women, youth, and traditional leaders as agents of reconciliation. Trauma-healing sessions and storytelling initiatives will foster collective recovery, reducing resentment and creating emotional space for forgiveness. Reinforcing norms of cooperation and mutual respect, will lay the foundation for long-term social cohesion. This approach will contribute directly to the peacebuilding pillar of the FFO funding concept by addressing both the root causes and consequences of conflict; trauma, exclusion, and mistrust. - Alignment with International and National frameworks: (1) UN Security Council Resolutions 1325 and 2250: The project will advance both agendas by ensuring that women and youth are central to peace decision-making and conflict prevention. (2) South Sudan Revitalised Peace Agreement (2018) and National Youth Policy (2022): The initiative will translate these frameworks into tangible local action, making peace inclusive, participatory, and gender-responsive. (3) FFO’s Global Mandate: It embodies the FFO’s guiding principle that civilian conflict management succeeds when local and international actors cooperate to address political, social and structural causes of violence. - Lasting Contribution By project completion, Greater Jonglei will have: - Ten institutionalised peace committees officially linked to county authorities; - A functioning youth mediation network active in early warning; - Three locally negotiated peace accords with measurable adherence; - A demonstrable 20% reduction in revenge attacks (UNMISS incident data); - A regional model for community-led stabilisation replicable in other high-risk areas of South Sudan. Through these outputs, the project will transform isolated peace efforts into an integrated local peace architecture; thereby providing a tangible, replicable model of crisis prevention and peacebuilding fully consistent with the Federal Foreign Office’s strategic objectives.

| Monitoring – Regular review of the progress of the project and the impact of the activities |  |
| --- | --- |
| With what measures and at what intervals do you check the progress of the project? | Monitoring will be continuous, participatory, and data-driven, guided by I-WIN’s internal M&E Framework and the zivik MOVIE methodology. Planned monitoring measures and intervals: - Baseline Assessment (May 2026): - Conducted across all payams in Bor South County to document existing peace mechanisms, inter-communal relations, IDP dynamics, and incident data. - Includes gender- and age-disaggregated perception survey (minimum 400 respondents). - Monthly Activity Monitoring (May–December 2026): - Routine tracking of all training, dialogue, and caravan activities using attendance forms, photos, and GPS logs. - Monthly reports summarise outputs, progress toward outcomes, and deviations. - Quarterly Reflection and Learning Workshops (July, October, December 2026): - Facilitators, youth mediators, and peace committees review progress, identify lessons, and adjust strategies. - Involves joint analysis with chiefs, women leaders, and county authorities. - Mid-Term Review (August 2026): - Participatory mid-term with 25 stakeholders. Participants include youth mediators, peace committee chairs, county officials, and UNMISS representatives; comparing progress against baseline and MOVIE milestones. - Informs adaptive planning for second half of implementation. - End-Line Evaluation (December 2026): - External assessment combining surveys, focus groups, and outcome harvesting. - Compares baseline and end-line indicators (trust levels, mediation cases, incident frequency). Monitoring will use triangulated sources: quantitative surveys, qualitative interviews, observation checklists, and UNMISS/Protection Cluster reports. All data is to be digitised using KoboToolbox and analysed monthly to feed into project dashboards and management decisions. |
| - Who carries out these measures? - How do you reflect on the role of your organisation in the project context and how do you deal with this during the course of the project? | a) Monitoring responsibilities are distributed across I-WIN’s project team for accountability and accuracy: - M&E Officer (Lead): Will oversee planning, tools, data collection, and reporting to ifa/zivik. - Field M&E Focal Persons (5): Collect monthly field data and validate activity reports with signatures from local chiefs or committee chairs. - Programme Manager: Reviews progress reports and authorises adaptive decisions. - External Evaluator: Conduct independent end-line evaluation for objectivity. - Community Monitors: Youth mediators to collect basic feedback from communities and forward through WhatsApp and Kobo forms. Each level to ensure data verification (“four-eyes principle”) to prevent bias and misreporting. b) I-WIN to continuously reflects on its dual role as both facilitator and capacity builder rather than as a decision-maker. During each quarterly reflection workshop, staff and community actors to analyse: - How I-WIN’s facilitation methods influence local power dynamics; - Whether its interventions uphold neutrality, inclusion, and local ownership; - Whether gender and youth representation remain balanced and meaningful. Feedback from partners (chiefs, women’s groups, county peace offices) is to be formally reviewed and integrated into subsequent activity plans. In case of perception of bias or elite influence, I-WIN will adjust participation modalities-rotating facilitators or co-facilitating with neutral community members. This self-reflective practice will ensure that I-WIN’s engagement strengthens, rather than overshadows, local peace leadership and reinforces the subsidiarity principle central to the Federal Foreign Office’s peacebuilding approach. |
| What are the objectives and benefits of your chosen measures? | Objectives: - To systematically measure whether activities lead to the desired behavioural change among key actors. - To enable adaptive management-quickly addressing obstacles or risks. - To generate credible evidence for donors, communities, and policymakers. Benefits: - Ensures accountability to both beneficiaries and funders. - Encourages community ownership by involving peace committees in data collection and reflection. - Strengthens institutional learning for I-WIN and partners, creating a replicable peacebuilding model. - Produces tangible documentation (case studies, photos, outcome maps) for communication and policy influence. Through these measures, monitoring becomes a learning and transformation process; not merely compliance. It will ensure that the project continuously aligns with the MOVIE theory of change and contributes demonstrably to crisis prevention, stabilisation, and peacebuilding in Greater Jonglei. |

| Evaluation – Overall review of the project (planning, monitoring, control, findings, effectiveness) |  |
| --- | --- |
| What measures do you use to check the effectiveness of the project? | The evaluation approach is to combine quantitative measurement, qualitative learning, and participatory validation, guided by the zivik MOVIE manual and I-WIN’s internal evaluation policy. - Baseline vs. End-line comparison: - Quantitative data (e.g., number of conflicts, perception of safety, inclusion levels) collected during the baseline in April 2026 will be compared to end-line data in December 2026 to measure changes in conflict dynamics, trust levels, and participation. - Outcome Harvesting: - Facilitators and M&E officers will document observable behavioural changes among youth mediators, peace committees, and local leaders. Each “change story” will be validated by at least two independent sources (e.g., UNMISS Civil Affairs, county peace offices). - Perception Surveys and Focus Group Discussions: - Conducted mid-term and at project end to assess shifts in inter-ethnic trust, gender inclusion, and community confidence in local peace structures. - Conflict Trend Analysis: - UNMISS and Protection Cluster data will be analysed to determine quantitative reductions in inter-communal incidents, revenge killings, and cattle raids in Bor South County and surrounding areas. - Institutional Assessment: - Review of whether peace committees have been formally recognised by county administrations and incorporated into local peace planning frameworks. - Cost-Effectiveness and Replicability Review: - Analysis of cost per mediated conflict and cost per beneficiary reached, with recommendations for scaling to other regions. This multi-layered approach will ensure that evaluation goes beyond output counting to verify real behavioural and structural change; core to the Federal Foreign Office’s crisis-prevention agenda. |
| - Who carries out these measures? - What is your own role? | - Responsibility Structure: - External evaluator: A qualified South Sudan–based peacebuilding consultant or firm will be competitively procured in line with I-WIN’s procurement policy and zivik guidelines. The evaluator will design and lead the final evaluation, ensuring objectivity and methodological rigour. - M&E Officer: Coordinates the entire evaluation process, ensures data availability, supervises enumerators, and liaises with field offices. - Programme Manager and Project team: Provide logistical support, access to records, and facilitate stakeholder participation in validation workshops. - Stakeholder Validation group: Representatives from peace committees, chiefs, women’s groups, and youth networks will review findings for accuracy and provide contextual interpretation. - I-WIN’s Role: Acts as commissioning organisation, ensuring adherence to donor standards, safeguarding principles, and timely submission of the final report to ifa/zivik. I-WIN will also integrate recommendations into its 2027–2029 strategy for replication. All data collection staff and enumerators will sign confidentiality and data-protection agreements in line with GDPR and I-WIN’s internal Data Protection Policy (2024). |
| What are the objectives and benefits of your chosen measures? | Objectives: - To determine the extent to which project outcomes and impact indicators were achieved and to understand causal linkages. - To measure the contribution of youth- and women-led structures to the reduction of violence and improved social cohesion. - To identify strengths, challenges, and lessons for scaling the model in Upper Nile, Warrap, and Lakes States. - To provide evidence-based accountability to beneficiaries, partners, and the German Federal Foreign Office. Benefits: - Learning and Adaptation: Generate practical insights for refining I-WIN’s peacebuilding methodology and improving similar future interventions. - Transparency and Accountability: Provide credible, externally validated evidence to ifa/zivik, donors, and communities that resources were used effectively. - Empowerment and Ownership: Involving beneficiaries in evaluation will strengthen local capacity for self-assessment and participatory decision-making. - Replication Potential: The evaluation will produce a concise policy brief highlighting key success factors, cost-efficiency, and transferability to other conflict-affected regions of South Sudan. |

| Achievement of objectives (target-performance comparison) |  |
| --- | --- |
| For the summary report on project funding, you are asked to carry out a target-performance-comparison. - How will you assess the success of the project carried out, both qualitatively and quantitatively, especially at the outcome level? - How can the success be measured? | a) Success will be assessed through a combination of quantitative performance indicators and qualitative evidence of behavioural and structural change, consistent with the MOVIE approach and the FFO’s funding requirements for crisis prevention and stabilisation. Quantitative Assessment - Participation and Representation - Target: 80 youth trained as mediators (≥ 50 % women). - Target: 6 functional inter-ethnic peace committees (10 members each; ≥ 50 % women). - Target: 10 inclusive dialogue forums conducted with ≥ 1,000 total participants. - Target: At least 3 local peace agreements signed and monitored. - Conflict Reduction and Stability Indicators - Target: ≥ 20 % reduction in inter-communal revenge attacks and cattle-raid incidents in Bor South County (verified through UNMISS and Protection Cluster data). - Target: ≥ 60 % of surveyed participants report improved inter-ethnic trust and sense of security compared with baseline. - Awareness and Outreach - Target: 8 radio programmes, 3 podcasts and 3 mobile peace caravans reaching ≈ 150,000 listeners/viewers. - Target: ≥ 60 % listener recall rate of peace and coexistence messages (survey data). - Institutionalisation - Target: 5 signed MoUs between peace committees and county administrations integrating them into official peace structures. Qualitative Assessment - Behavioural Change - Observable shift among youth from participation in armed groups to peace-promoting roles, evidenced by community feedback and outcome-harvesting interviews. - Attitudinal Transformation - Improved inter-communal relationships and willingness to cooperate across ethnic lines, documented through focus groups and case studies. - Gender and Inclusion Impact - Women and young women actively mediating disputes and assuming leadership in committees; stories of empowerment and acceptance recorded. - Governance and Legitimacy - County authorities increasingly consult community peace structures in decision-making, showing institutional acceptance and ownership. These qualitative and quantitative measures will be triangulated through surveys, monitoring data, UNMISS security trend analysis, observation reports, and external evaluation findings to determine achievement at the outcome level. b) Success will be measured using the following methods and tools: - Baseline and End-line Surveys: Quantify change in community perceptions of safety, trust, and inclusion. - Conflict-Incident Tracking: Compare UNMISS and Protection Cluster records pre- and post-intervention. - Outcome Harvesting: Document and verify stories of behavioural change among youth, women, and leaders. - Peace Committee Logs: Track mediation cases, resolutions reached, and early-warning alerts submitted. - Focus Group Discussions: Gather nuanced perspectives on reconciliation and gender dynamics. - External Evaluation Metrics: Independent consultant applies the MOVIE framework to assess effectiveness, sustainability, and replicability. Measurement Frequency: Baseline (April 2026), mid-term (August 2026), end-line (December 2026). Success is to be confirmed when outcome-level indicators (behavioural change, trust, institutional recognition) meet ≥ 80 % of their targets and when external evaluation rates overall project effectiveness as “good” or “very good.” |
| What distinguishes the project from others? Are there e.g. innovative aspects, unique features, distinctive characteristics you can highlight? | The project stands out among peacebuilding initiatives in South Sudan through several innovative and distinctive features: - Youth and Women-led mediation architecture: Rather than using external mediators, the project will empower community members; particularly women and youth, to serve as frontline peace actors. This will reverse traditional hierarchies and ensures sustainability. - Flood-adaptive Peace Caravans: Mobile outreach teams using boats and canoes during the rainy season will enable continuity of peace activities even in hard-to-reach areas, linking peacebuilding to climate adaptation. - Integrated trauma-healing and mediation training: Each mediation module to include psychosocial components, addressing trauma as both a root cause and barrier to reconciliation; a gap often missed in similar projects. - Digital monitoring and early warning: Kobo Toolbox and WhatsApp groups to link community committees with county authorities and UNMISS for real-time reporting of emerging conflicts; creating a locally driven early-warning network. - Cultural and media-driven social change: Radio dramas, songs, and theatre performances to broadcast in Dinka, Nuer, and Murle languages to promote non-violent masculinity and cross-cultural empathy, turning local art into a peace tool. - Formal institutional linkage: Through MoUs with local government, the project will ensure that committees are embedded within official governance structures; bridging the gap between informal community peace efforts and formal state mechanisms. - Replication potential: Designed as a scalable pilot, the model can be adapted to other conflict-affected states such as Upper Nile and Warrap, contributing to national stabilisation and the localisation agenda. |

| Action plan Who does what, with whom and when, in order to achieve the change processes among the key actors of the project? |  |  |  |
| --- | --- | --- | --- |
| What? | Who? | When? | Remarks |
| List activities with precise information on the individuals addressed and quantities (frequency, persons involved, days, etc.) | Responsible for implementation | Specific date / time period | Regarding implementation |
| Activity 01: Inception, mobilisation & conflict mapping a) Project launch in Bor Town with local authorities, UNMISS, and community representatives. b) Stakeholder consultations across Bor South County payams (including displaced communities from northern Jonglei). c) Participatory conflict mapping The M&E Officer will travel for 12 days to conduct the baseline survey across Bor South County payams and IDP sites (2 days per payam × 6 payams plus travel days). This covers administration of 400 KoboToolbox questionnaires, community FGDs, and conflict mapping consultations. | Project Officer, M&E Officer | May 2026 | Aim: To initiate the project, establish legitimacy, and build a shared understanding of the conflict context. Topics/issues addressed: Stakeholder identification, local conflict drivers, early-warning gaps, population movements, youth/women exclusion patterns, seasonal/climate stressors. To introduce project objectives, roles, and expectations to all stakeholders. Consultations to identify trusted mediators, local grievances, early-warning gaps, and conflict host-spots in each payam. Baseline Survey to assess perceptions of safety, inter-ethnic trust, attitudes toward youth/women leadership, and existing dispute-resolution pathways. Establish the benchmark for all outcome-level measurements and ensure early stakeholder ownership. Establish stakeholder buy-in and baseline data. Identify flashpoints and potential mediators. Linked to Key Actors 1-4. Security Risk & Mitigation: Low risk. Inception activities to take place in Bor town (UNMISS-secured). Stakeholder consultations held in accessible payams confirmed by OCHA inter-agency assessment (5 February 2026). Baseline enumerators to travel in pairs during daylight hours only. UNMISS security briefing to precede all field movements. |
| Activity 2: Recruitment and selection of youth mediators a) Community nomination meetings (chiefs, women’s leaders, churches). b) Vetting of 80 youth (14–35 yrs; 50 % women) for training. | Project Officer, M&E Officer | May 2026 | Aim: To transparently select a trusted, inclusive, and competent cohort of 80 youth mediators. Topics/issues addressed: Selection criteria (neutrality, integrity, and representation), gender balance, clan/ethnic inclusiveness, preventing elite capture, ensuring local legitimacy. Selection to be based on community trust, literacy, neutrality, gender balance, and clan/ethnic representation. Meetings are to ensure transparency and protect against elite capture. The activity will identify candidates for mediation training and document their motivations, prior roles and expected contributions. Ensure diversity across Dinka, Nuer, Murle groups. Build legitimacy of participants. Key Actor 1. Security Risk & Mitigation: Low risk. Recruitment to be conducted through existing community networks (chiefs, women’s associations) in Bor South payams. No large gatherings required. Vetting coordinated with UNMISS Civil Affairs to ensure conflict-sensitive selection. |
| Activity 3: Training of youth mediators in mediation & trauma healing – Two 5-day modular trainings (Bor Town, two cycles). – Topics: conflict analysis, mediation skills, psychosocial first aid, gender inclusion, Do No Harm, UNSCR 1325 & 2250, reporting tools. – Certificates issued. A lead Trainer/Coach is to be engaged as a consultant for this activity (Youth Mediator Training). The consultant will conduct two 5-day modular training sessions (Cycle 1 and Cycle 2) in Bor Town for 35 youth mediators per cycle (70 total). | Lead Trainer, Psychosocial Specialist, Project Officer | May/June 2026 | Aim: To equip youth with mediation, negotiation, trauma-healing, and protection skills. Topics/issues addressed: Mediation steps, conflict analysis tools, trauma-informed approaches, GBV referral pathways, Do No Harm, UNSCR 1325/2250, psychosocial first aid, managing inter-ethnic grievances. Participants per training: 35 youth mediators per training session There are two 5-day modular trainings: - Training 1 – Bor town (Cycle 1): 35 youth - Training 2 – Bor town (Cycle 2): 35 youth Total trained mediators: 70 youth mediators (50% women, multi-ethnic, 14-35 years). Strengthen youth technical capacity and confidence as local peacebuilders. Key Actor 1. Security Risk & Mitigation: Low risk. Training to be held at secure venue in Bor town with UNMISS proximity. Participants to travel from within Bor South County payams only. Two 5-day cycles will reduce prolonged absence from communities. Contingency: sessions will be split into smaller groups if security deteriorates. |
| Activity 4: Establishment of inter-ethnic peace committees – 6 committees formed (1 per payam) with balanced ethnic/gender representation (5 women, 5 men per committee). Each peace committee meeting will last 2 days. There are 6 committees × 1 meeting each during the formation phase = 6 meetings × 2 days = 12 committee-days. – Conduct inaugural orientation and constitution drafting. | Project Staff, Volunteer | May/June 2026 | Aim: To institutionalise sustainable, community-rooted peace structures across Bor South County (6 payams). Topics/issues addressed: Committee constitution, mandates, reporting channels, diversity representation, early-warning roles, accountability rules, gender participation. Committee members are to be selected through a transparent, community-driven process where chiefs, women’s groups, and youth structures will nominate trusted individuals who are to then be vetted for neutrality, integrity, basic literacy, local legitimacy, gender balance, and representation of all ethnic/clan groups. Final lists are to be validated publicly to prevent elite capture. Each of the 6 committees will hold one formal meeting per month, with additional ad-hoc meetings during heightened tensions. The committees will play a central role in community-level peace governance: mediating disputes, providing early-warning information, monitoring adherence to peace agreements, facilitating trauma-informed dialogue, supporting referrals for GBV survivors, conducting peace sensitisation, and coordinating with County Peace Offices and UNMISS Civil Affairs. They will function as the primary bridge between informal community actors and formal local authorities, ensuring sustainability of peace structures beyond the project. Institutionalises inclusive local peace mechanisms. Key Actor 2. Security Risk & Mitigation: Low–moderate risk. Committee formation in 6 payams will require field travel. Mitigated by daylight-only movement, UNMISS coordination, and local chief engagement. Security Decision Gate review at month 2 will assess conditions before committees are inaugurated in remote payams. |
| Activity 5: Monthly committee meetings (8) & mentoring – Facilitation of monthly meetings (8 in total); agenda includes mediation reports, early-warning briefs, coordination with county offices. – Continuous mentorship by I-WIN technical team. | Volunteer, M&E Officer | May–December 2026 | The Peace Committees are to serve as the primary community-level mechanism for conflict prevention, mediation, and coordination between informal and formal peace actors. Their core tasks will include monitoring emerging tensions and providing early-warning alerts; mediating disputes related to cattle movement, land, resource sharing, youth clashes, and returnee reintegration; supporting implementation and monitoring of inter-communal peace agreements; conducting community sensitisation on peaceful coexistence, trauma healing, and GBV prevention; and liaising with County Peace Offices, chiefs, and UNMISS Civil Affairs to ensure information flow and timely response. They also will document cases, maintain meeting records, and report monthly to ensure accountability and consistency in local peace efforts. The committees are to be essential because they fill a critical gap in local peace infrastructure where state presence is weak, inter-community trust is low, and formal justice systems are often inaccessible or ineffective. Their existence will ensure that conflict is addressed early and locally, reducing the likelihood of escalation into wider violence. They will draw legitimacy from inclusive representation; youth, women, elders, and diverse ethnic/clan groups; making them trusted, culturally anchored actors capable of mobilizing communities and sustaining peace beyond the project period. By serving as the link between communities and county authorities, they will reinforce local ownership, strengthen social cohesion, and provide a sustainable, community-driven structure for conflict resolution. Maintains momentum and documentation of cases handled. Key Actor 2. Security Risk & Mitigation: Low risk. Meetings to be held in community venues within payams. Field coordinators to maintain regular communication with UNMISS and County Peace Desk for security updates. Meetings to be rescheduled if localised tensions arise. |
| Activity 6: Community dialogue forums – 10 dialogue events held across Bor South County payams. Each dialogue lasts one day with 100 participants per forum. – Themes: resource sharing, youth & women leadership, reconciliation, trauma-healing circles. – Translation provided in Dinka/Nuer/Murle. | Project Officer, Psychosocial Specialist | July–November 2026 | Aim: To create safe, structured spaces for communities to address grievances and rebuild trust. Topics/issues addressed: Land/pasture disputes, cattle migration tensions, returnee integration, youth–elder relations, women’s leadership barriers, trauma narratives, forgiveness practices. Participants: Each dialogue to includes 100 participants, drawn from: - Chiefs and traditional authorities - Women leaders and women's associations - Youth representatives (including trained mediators) - Religious leaders - Cattle camp leaders and elders - Persons with disabilities - Returnees and IDPs - Local administrators and county peace officials - Representatives from different ethnic/clan groups to ensure balance Why the Dialogues: The dialogues aim to address key inter-communal grievances, rebuild trust, and negotiate peaceful solutions to long-standing tensions. They will provide a safe and structured platform for communities to openly discuss issues such as land and pasture disputes, cattle migration routes, revenge attacks, youth–elder dynamics, trauma and psychosocial wounds, women’s exclusion from decision-making, GBV-related concerns, and climate-related pressures that exacerbate conflict. The sessions will help communities reach shared understandings, identify practical solutions, commit to non-violence, and strengthen social cohesion across ethnic lines. Builds inter-ethnic trust and consensus on grievances. Key Actors 2 & 3. Security Risk & Mitigation: Moderate risk. Large gatherings (100 participants) will require careful venue selection and UNMISS liaison. Mitigated by: holding forums in Bor town and accessible payam centres; UNMISS Force patrols near venues; separate women-only/youth-only sessions where mixed gatherings pose risk; Security Decision Gate at month 5 to review continuation. |
| Activity 7: Negotiation and signing of community peace agreements – 2 local peace pacts ceremonies, each lasting 2 days. Each ceremony will have 30 participants (chiefs, elders, women leaders, youth representatives, County Commissioner, UNMISS CAD, and peace committee members from the relevant ethnic groups) - Public endorsement events and radio coverage will accompany each ceremony – Agreements include provisions for cattle-movement corridors and GBV referral cooperation. | Project Officer, M&E Officer | September–November 2026 | Aim: To formalise commitments to peaceful coexistence and reduce the risk of inter-communal violence. Topics/issues addressed: Migration corridor agreements, anti-raid commitments, GBV cooperation, cross-border mobility, sanctions for violations, joint problem-solving mechanisms. The peace agreements are to be negotiated and signed between the specific inter-communal groups in conflict within the project area. These typically include: - Dinka–Nuer communities, - Nuer–Murle communities, and - Dinka–Murle communities, depending on the county and the conflict dynamics identified during mapping. Each agreement is co-signed by chiefs, elders, women leaders, youth representatives, and the County Commissioner, ensuring broad legitimacy and community endorsement. Role of UNMISS Civil Affairs Division (CAD): UNMISS CAD will play a neutral facilitation and advisory role throughout the negotiation process. They will: - Provide technical guidance on mediation procedures and inclusive negotiation; - Ensure the process is impartial and free from political interference; - Support confidence-building between hostile groups; - Help frame agreements in a way that aligns with county, national, and UN stabilisation priorities; - Strengthen linkages between community peace structures and formal governance systems; - Provide security analysis and conflict-trend insights to inform realistic commitments; - Observe and legitimize the signing of the pacts, increasing accountability and follow-up. UNMISS CAD will not dictate the content of the peace pacts; instead, they will ensure the process is fair, transparent, and safe, reinforcing community ownership and long-term sustainability. Formalises community commitments; enhances ownership and visibility. Key Actors 2 & 4. Security Risk & Mitigation: Moderate risk. Peace ceremonies to involve cross-clan gatherings. Mitigated by UNMISS Civil Affairs co-facilitation, neutral venue selection, advance conflict analysis of attending groups, and daylight scheduling. Agreements to address localised inter-communal disputes, not the broader military conflict. |
| Activity 8: Mobile Peace Caravan – 3 tours reaching 15 priority villages and IDP sites using trucks/canoes depending on season. Each caravan tour will last 3 days and reach 200-300 participants per tour. – Activities: theatre, sports, music, storytelling, peace murals. – Distribution of IEC materials on reconciliation & GBV prevention. | Youth Caravan Team (10 volunteer youth mediators who were trained in Activity 3), Project Officer, M&E Officer | July–November 2026 | Aim: To spread peace messages and reach remote villages inaccessible to formal peace structures. Topics/issues addressed: Peace messaging, trauma awareness, reconciliation stories, GBV prevention, climate adaptation (flood preparedness), youth leadership visibility. Chronological Order of Activities & Sub-Activities: - July 2026 – Planning & Route Mapping: - Caravan team meets with chiefs, women leaders, and county authorities to agree on safe routes, identify high-risk villages, and consider climate barriers (flooded roads, rising water levels). - July 2026 – Production of Messages & Materials: - Youth mediators and the Communications Officer develop theatre scripts, storytelling segments, climate-risk messages, and co-existence content. - IEC materials (peace posters, flyers, brochures) are printed in Dinka, Nuer, and Murle. - August 2026 – Caravan Tour 1 (Dry-season access): - Performances and sensitisation events delivered in accessible villages before rains restrict movement. - September 2026 – Adaptation of Routes Based on Flood Patterns: - Using local knowledge, UNMISS security updates, and climate-risk mapping, the team adjusts routes to reach communities with increasing flood vulnerability. - October 2026 – Caravan Tour 2 (Mixed access): - Teams use a combination of trucks and boats to reach semi-flooded areas, integrating climate-adaptation messages. - November 2026 – Caravan Tour 3 (Late-flood season): - Boats/canoes used to reach isolated settlements. Activities emphasise resilience, safe migration, and cooperation during climate-induced displacement. - Continuous – Documentation & Feedback Collection: - Feedback captured from villagers, chiefs, youth, and women for improved messaging and adaptive planning. Integration of Climate Adaptation: The caravan will include climate-sensitive peace messaging to help communities understand how floods, drought cycles, pasture loss, and water shortages contribute to inter-ethnic tensions. Messages promote cooperative resource sharing, safe seasonal migration, early-warning reporting, and joint flood preparedness. The route itself is adapted based on flood patterns, ensuring access to the most climate-vulnerable villages. Promotes peace messages to flood-isolated areas; integrates climate adaptation. Key Actors 1, 3, 5. Security Risk & Mitigation: Moderate risk. Caravans to reach remote areas. Mitigated by: flood-adapted transport (truck dry season, canoe rainy season); pre-approved routes cleared with UNMISS; local chief advance notification; daylight travel only; real-time communication via satellite phone. Security Decision Gate at months 2, 5, and 7 to assess route safety. Caravan to be suspended if UNMISS advises against travel to specific payams. |
| Activity 9: Radio & media engagement 8 radio programmes and 3 podcasts in local languages (Dinka, Nuer, Murle) on Radio. – Features interviews, call-in sessions, and success stories of youth mediators. It total 8 radio programmes, 3 short podcasts & 1 video documentary are produced. | Contracted radio service provider, Youth Hosts (trained mediators from Activity 3), M&E Officer | July–December 2026 | Aim: To amplify peace messages and shift narratives toward unity and coexistence. Topics/issues addressed: Mediation success stories, peaceful coexistence, cultural understanding, GBV awareness, youth & women leadership, climate-related conflict drivers. Content is produced jointly by trained youth mediators, the Communications Officer, and a professional Media Producer, with chiefs and women leaders joining as guests to ensure legitimacy. Ten radio programmes, three podcasts, and a short documentary will reach an estimated 150,000 people across Bor South County through FM radio stations, youth listening groups, cattle camps, and online platforms. Media content is published by local stations and the I-WIN Communications Unit on Facebook, YouTube, WhatsApp groups, and the I-WIN website. Topics include peaceful coexistence, mediation successes, women/youth leadership, GBV prevention, trauma healing, early-warning, and climate-related conflict drivers. All content undergoes conflict-sensitive editing and adheres to Do No Harm and zivik visibility standards. Amplifies behavioural change messages and visibility. Key Actor 5. Security Risk & Mitigation: Low risk. Radio production in Bor town studios. Broadcasting via existing FM infrastructure. No field exposure required for production. Content to be reviewed for conflict sensitivity before broadcast. |
| Activity 10: Leadership round-tables with county authorities – 5 county-level dialogues/roundtables with each leadership roundtable lasting 1 day and is to be attended by 25-30 participants (county authorities, chiefs, peace committee leaders, women and youth representatives, religious leaders, and UNMISS CAD). – Draft and sign MoUs recognising peace committees as local advisory bodies. – Joint review of early-warning data. | Project Officer, M&E Officer | September–November 2026 | Aim: To strengthen formal–informal linkages and secure government buy-in for local peace structures. Topics/issues addressed: Early-warning integration, peace agreement follow-up, MoU commitments, coordinating roles, gender safeguards, support to committees. Each leadership roundtable brings together 25-30 participants, including county authorities, chiefs, peace committee leaders, women and youth representatives, religious leaders, and UNMISS CAD. The meetings review early-warning data collected monthly from Peace Committees (primary source), chiefs and community structures, County Peace Offices, and UNMISS CAD conflict analyses. The aim is to link community-level alerts with formal decision-making, follow up on peace pact implementation, agree on joint responses to emerging tensions, and strengthen coordination between informal and formal peace structures. Fosters formal collaboration and sustainability. Key Actors 2 & 4. Security Risk & Mitigation: Low risk. Roundtables to be held in Bor town with County Commissioner’s office. UNMISS representatives to be invited as observers. MoU signingto be a formal institutional event with minimal security exposure. |
| Activity 11: Monitoring, learning, and adaptive management – Monthly data collection; quarterly reflection workshops; documentation of case studies. – Integration of lessons into subsequent activities. | M&E Officer, Volunteer | May–December 2026 | Aim: To track progress, identify issues early, and ensure the project adapts to evolving conflict dynamics. Topics/issues addressed: Data verification, committee performance, mediation cases, gender inclusion, risk tracking, Do No Harm review, coordination challenges. Each quarterly reflection workshop will last one full day (8 hours) and bring together 25 participants, including the M&E Officer, Programme Manager, Field Coordinators, 1 representative from each Peace Committee, women and youth leaders, selected chiefs, and County Peace Office staff. The workshops will review implementation progress, verify data, analyse challenges and emerging risks, and agree on adaptive measures to improve performance and coordination. Ensures responsiveness and continuous improvement. All Actors. Security Risk & Mitigation: Low risk. M&E Officer to use KoboToolbox for remote data collection where possible. Field visits to follow UNMISS security advisories and daylight-movement protocols. Security SitReps to be submitted weekly to ifa/zivik. |
| Activity 12: Mid-term review workshop – One-day mid-term review that is to be a participatory workshop, including 25 participants: Programme Manager, M&E Officer, Field Coordinators, one representative from each Peace Committee, chiefs/deputy chiefs, women leaders, youth mediators, and County Peace Office officers, with UNMISS CAD as observers. The workshop will last 1 day (8 hours) in Bor town and take stock of the project progress, challenges, and opportunities for adaptation. | Project Officer, M&E Officer | August 2026 | Aim: To assess overall progress and refine implementation strategies for the remaining months. Topics/issues addressed: Baseline vs mid-term comparison, committee functionality, inclusion gaps, conflict trend shifts, need for design adjustments. The mid-term review workshop will bring together 25 participants, including the project team (Programme Manager, M&E Officer, Field Coordinators), one representative from each Peace Committee, chiefs or deputy chiefs, women leaders, youth mediators, and County Peace Office officers, with UNMISS CAD invited as observers. Mid-project learning checkpoint. All Actors. Security Risk & Mitigation: Low risk. Single-day workshop in Bor town. Participants to be drawn from within Bor South County. Security Decision Gate review at month 5 to preceed mid-term, ensuring conditions are assessed before convening. |
| Activity 13: External end-line evaluation & dissemination a) Independent consultant conducts evaluation (surveys, FGDs, outcome harvesting).The external end-line evaluation will take 20 working days: 3 days inception, 7 days fieldwork (across Bor South County payams and IDP sites, involving 7 field trips), 5 days analysis and drafting, 2 days validation, and 3 days finalisation. b) Results shared in Bor town dissemination workshop. The dissemination workshop will last 1 day (8 hours) and gather 25 participants, including the External Evaluator, project leadership, one representative from each Peace Committee, chiefs, women leaders, youth mediators, County Peace Offices, and UNMISS CAD. | External Evaluator, M&E Officer | November–December 2026 | Aim: To provide an independent assessment of project outcomes, effectiveness, and sustainability. Topics/issues addressed: Outcome harvesting, case studies, conflict trend analysis, gender impact, sustainability prospects, institutional coordination. The external end-line evaluation will take 20 working days (3 days inception; 7 days fieldwork; 5 days analysis & drafting; 2 days validation; 3 days finalisation). It will use a mixed-methods approach including interviews, FGDs, document review, observation, and comparison of baseline vs. end-line indicators. Data is to be triangulated across committees, chiefs, women/youth leaders, county authorities, and UNMISS CAD. A validation workshop with 25 stakeholders will ensure accuracy and ownership before final report submission. The dissemination workshop in Bor will gathers 25 participants, including the External Evaluator, project leadership, one representative from each Peace Committee, chiefs, women leaders, youth mediators, County Peace Offices, and UNMISS CAD. The workshop will last one full day (8 hours) and is to be used to present evaluation findings, validate results, discuss lessons learned, and agree on sustainability recommendations. Measures effectiveness, documents lessons, informs scale-up. All Actors. Security Risk & Mitigation: Low risk. External evaluator to use local enumerators for field data collection across payams. Validation workshop to be held in Bor town. UNMISS security clearance to be obtained for all evaluator movements. Time buffer to be built into schedule for security delays. |
| Activity 14: Project closure & sustainability planning – Development of transition plan with county authorities and community committees. – Formation of voluntary Peace Sustainability Network for continuous dialogue beyond funding. | Project Officer, M&E Officer | December 2026 | Aim: To institutionalise learning, strengthen post-project ownership, and ensure sustainability. Topics/issues addressed: Sustainability roadmap, handover to committees/county authorities, post-project monitoring system, formation of Peace Sustainability Network. A one-day (8-hour) sustainability planning meeting is to be held in Bor with the Executive Director, Programme Manager, M&E Officer, Field Coordinators, one representative from each Peace Committee, County Commissioners/Peace Offices, chiefs, women leaders, youth representatives, and UNMISS CAD. The session will review lessons learned, committee functionality, and remaining risks, and jointly develop a transition plan outlining post-project roles, reporting lines, early-warning responsibilities, and the formation of a Peace Sustainability Network to ensure continuity beyond the project period. Ensures ownership and post-project continuation. Key Actors 2 & 4. The Peace Sustainability Network operates through three zero-cost channels — (1) WhatsApp group (primary) linking the 6 peace committee chairs, M&E Officer, and I-WIN Executive Director for quarterly check-ins, case-sharing, and early-warning alerts; (2) Quarterly in-person meetings rotating between Bor Town and payam centres, hosted on voluntary basis post-project; (3) Shared Google Drive folder for documents, minutes, and learning materials. No additional financial plan costs required. Security Risk & Mitigation: Low risk. Closure activities to be conducted in Bor town. Handover to County Peace Desk and peace committees through formal meetings. No large field movements required. |

Risks and assumptions (context  project) - Which political and societal contextual factors could hinder, prevent or support the intended activities and effects? - In particular, how could one deal with the risks of the project?

Risk / Assumption; Potential Effect on the Project; Mitigation / Response Strategy. 1. Renewed armed clashes or inter-communal violence in Bor South County; May restrict access to field locations, delay implementation, or endanger participants and staff.; Continuous coordination with UNMISS Civil Affairs and County Peace Desks for security updates; flexible scheduling of activities; insurance and contingency planning for staff movement.. 2. Seasonal flooding and poor road conditions; Transportation and access to remote communities become impossible during heavy rains, disrupting dialogue and caravan schedules.; Use of flood-adapted peace caravans (boats and canoes); pre-positioning of materials in dry season; remote facilitation using radio and WhatsApp where physical access is blocked.. 3. Political interference or elite capture of peace committees; May undermine neutrality and community trust; risk of politicisation of local structures.; Transparent and participatory selection of committee members with oversight from chiefs, women’s associations, and youth representatives; adherence to I-WIN’s Code of Conduct and neutrality policy; regular public reporting of committee activities.. 4. Cultural resistance to women’s and youth leadership; Reduces women’s participation and legitimacy of gender-balanced structures; may reinforce patriarchal norms.; Community sensitisation and male-ally dialogues prior to training; endorsement of women mediators by chiefs and clergy; continuous awareness via radio on the value of inclusive leadership.. 5. Inflation and market volatility; Increases operational costs and may reduce scope of outreach activities.; Maintain a 3 % contingency buffer in budget; quarterly budget reviews; use of framework agreements with suppliers to lock prices.. 6. Staff turnover or burnout; Loss of institutional memory and delays in activity delivery.; Ensure proper onboarding, mentorship, and rotation; maintain up-to-date documentation and shared databases; staff welfare and psychosocial support sessions.. 7. Limited cooperation from local authorities due to competing priorities; Slows integration of peace committees into formal governance structures.; Early engagement with County Peace Offices; formal MoUs clarifying roles; periodic joint review meetings and co-signing of peace agreements.. 8. Communication disruptions (radio signal, internet, mobile); Interrupts coordination and monitoring of field activities.; Establish backup communication channels (satellite phone, radio networks); use manual data forms when digital tools fail; synchronise field reports upon network restoration.. 9. Limited literacy among community participants; Affects record keeping and reporting by peace committees.; Use pictorial tools and oral reporting formats; provide basic literacy and record-keeping support; assign literate youth mentors to assist committees.. 10. Security incidents affecting external evaluator travel; May delay final evaluation or reduce coverage.; Allow time buffer in evaluation schedule; use local enumerators supported remotely by the evaluator; ensure UNMISS security clearance for all movements..

Possible unintended effects (project  context) - Which unintended positive or negative effects, e.g. those that promote change or exacerbate the conflicts, could arise from the project? - In particular, how could one deal with the unintended negative consequences?

Potential Unintended Effect; Type (Positive / Negative); Mitigation or Response Strategy. 1. Raised expectations for material or humanitarian assistance; Negative; Clearly communicate the project’s non-material focus during community mobilisation; coordinate messaging with UNMISS and other humanitarian actors to manage expectations.. 2. Increased public visibility of youth mediators leads to political manipulation or intimidation by armed groups; Negative; Apply I-WIN’s Security and Safeguarding Protocols; maintain neutrality; offer protective accompaniment through chiefs and UNMISS; rotate mediator visibility roles to reduce exposure.. 3. Spill-over demand for inclusion from non-targeted communities; Positive; Document interest as evidence of scalability; share approach with other counties through the State Peace Ministry and the Jonglei Peace Actors Forum for replication.. 4. Empowered women mediators face domestic backlash or community resistance; Negative; Conduct ongoing male-ally and family-sensitisation sessions; integrate local women’s leaders and faith figures as advocates; ensure community recognition ceremonies for women peacebuilders.. 5. Stronger community cohesion leads to informal migration of rival youth to peaceful areas seeking safety and livelihoods; Mixed; Monitor displacement trends; coordinate with local authorities to manage inflows; share best practices through peace caravans to new communities.. 6. Improved local stability may attract higher cattle concentration and competition for resources; Mixed; Integrate natural resource management dialogue with peace committees; link with FAO and WASH cluster interventions.. 7. Increased use of radio and social media could expose peace actors to online misinformation; Negative; Media Officer moderates broadcasts; counter false narratives quickly; promote verified information through local influencers and church leaders.. 8. Enhanced cooperation between ethnic groups inspires cross-county partnerships beyond project scope; Positive; Encourage documentation of joint activities as success stories; share lessons through DCA, UNMISS, and FFO networks for wider learning.. 9. Project success may lead to donor dependence by communities expecting continuation; Negative; Develop sustainability plan by mid-project; support committees to link with County Peace Funds and existing local NGOs for future support.. 10. Shift in local power dynamics may create tension with traditional authorities resistant to shared leadership; Negative; Maintain continuous dialogue with chiefs; frame youth and women inclusion as complementary to-not replacing-traditional authority..

While context factors such as insecurity, floods, and political volatility pose challenges, the mitigation and adaptation strategies will ensure operational continuity and staff safety. At the same time, positive unintended effects; such as spontaneous replication of peace structures and growing inter-ethnic cooperation, are expected and will be documented as lessons learned to strengthen future programming.